## University Park
UNIVERSITY PARK CAMPUS 2020
BUILDING NAME | PSU Proj.# | Permit # | L&I File# | Bldg.# | Description | Status | Date Sent to L&I | Date Returned | Level of Permit | Design Services / Outside Designer
1771 Pine Hall Rd. | 00-07338.00 | 202000756 |  | 0998-335 | Supplemental Heat Modifications | CANCELLED | 2020-06-22 | 2020-08-18 | 2 | OD | Jason Anderson Bill Waugh
1771 Pine Hall Rd. | 00-07338.00 | 202090950 | 540429 | 0998-335 | Stairwell Sprinkler Head Install | Building Permit | 2020-09-21 | 2020-10-19 | 1 | OD | Jason Anderson, Bill Waugjh
230 Building | 00-06924.00 | 202001228 | 541321 | 0965-002 | Cooling Tower Replacement | Building Permit | 2020-12-08 | 2021-01-05 | 2 | DS | Alan Zimmerman | A. Davis
3035 Research Dr. Library Depository | 00-06715.00 | 202000014 |  | 0912-000 | Palmer Museum Storage Space Revisions | C of O | 2019-12-27 | 2020-01-10 | 2 | OD | Christie Holloway |  | Ben
3035 Research Dr. Library Depository | 00-06715.00 | 202000058 |  | 0912-000 | Palmer Museum Storage Space Sprinkler | C of O |  | 2020-01-28 | 2 | OD | Christie Holloway
3035 Research Dr. Library Depository | 00-06715.00 |  |  | 0912-000 | Palmer Museum Art Storage - Fire Alarm | REJECTED |  | 2020-06-16 | 2 | OD | Christie Holloway
Academic Activities | 00-07281.00 | 202090296 |  | 0022-000 | RM 301 311 Ceiling Fans | Building Permit | 2020-02-21 | 2020-05-01 | 1 | DS | Christie Holloway | Bryan Ondrasik
Academic Projects | 00-07371.00 |  |  | 0407-000 | Lab 207 HVAC Reno | Rejected | 2020-10-20 | 2020-11-03 | 1 | DS | Mike Rupert | Bryan Ondrasik
Academic Projects | 00-07371.00 | 202001170 | 541014 | 0407-000 | Lab 207 HVAC Reno | Building Permit | 2020-11-03 | 2021-01-07 | 2 | DS | Mike Rupert | Bryan Ondrasik | Bryan Hayes
Ag Engineering | work order | 202091330 | 540862 | 0114-000 | Install Circuits in Fermentation Lab | Building Permit | 2020-10-22 | 2020-11-25 | 1 | DS | Jason Smith
Airport Aircraft Rescue & Firefighting | 00-05401.02 | 202000352 |  | 0963-032 | New Structure | Building Permit | 2020-03-05 | 2020-05-21 | 2 | OD | Kurt coduti |  | Thomas Woodring
Airport Fire Rescue Building | 00-07537.00 | 202001011 | 540275 | 0963-013 | Roof Top Fall Protection | Building Permit |  | 2020-10-19 | 2 | OD | Kurt Coduti |  | Thomas Woodring
Animal Diagnostics Lab | 00-06069.00 | 202000608 |  | 0169-002 | Dock Modification to Include Storage Facility | Building Permit | 2020-06-10 | 2020-07-28 | 2 | DS | Nathan Patrick | Kathy Poissant | Mike Kulbacki
ARL Test Site Bldg 1 | 00-05194.00 | 202000299 |  | 0996-015 | Domestic Water Mods | Building Permit | 2020-02-27 | 2020-05-04 | 2 | OD | Jeff Spackman
ARL Test Site Bldg 2 | 00-05194.00 | 202000370 |  | 0996-015 | Equipment Platform & Water Piping | Building Permit | 2020-03-03 | 2020-05-27 | 2 | OD | Jeff Spackman
ARL Test Site Bldg 3 | 00-06420.00 | 202000777 |  | in 0996-015 | Area of Rescue Revision | Building Permit | 2020-08-11 | 2020-08-20 | 2 | OD | Jeff Spackman
ARL West I | 00-06012.06 | 202000182 |  | 0996-019 | Radiological Booth ME | C of O | 2020-02-03 | 2020-03-03 | 2 | OD | Jeff Spackman
ARL West III | 00-06728.03 | 202000208 |  | 0066-000 | Roof Replacement | Building Permit | 2020-02-10 | 2020-03-11 | 2 | OD | Damian Rose
ARL West III | 00-06728.03 | 202000149 |  | 0066-000 | Restroom Reno | Building Permit | 2020-02-13 | 2020-02-21 | 2 | OD | Morgan VanOuse
ARL West III | 00-06728.03 | 202000762 |  | 0066-000 | Restroom Reno - Sprinkler | Building Permit |  | 2020-08-19 | 2 | OD | Morgan VanOuse
ARL West III | 00-06728.03 | 202000861 | 540173 | 0066-000 | Restroom Reno - Sprinkler Revision | CANCELLED |  | 2020-09-21 | 2 | OD | Morgan VanOuse
ARL West III | 00-06728.03 | 202001001 | 540502 | 0066-000 | Restroom Reno - Fire Alarm | Building Permit |  | 2020-10-19 | 2 | OD | Morgan VanOuse
Beam Hall | 00-06053.00 | 202090027 |  | 0211-000 | Domestic Hot Water Plumbing Upgrades | Building Permit | 2020-01-10 | 2020-01-28 | 1 | OD | Matt Vail
Beecher Dock House | 00-05489.01 |  |  | 0665-000 | Partial Basement Reno | REJECTED | 2019-12-17 | 2019-01-22 | 2 | DS | Ron Perttu | Forrest Rishel
Beecher Dock House | 00-05489.01 | 202001012 | 538194 | 0665-000 | Partial Basement Reno - Resubmission | Building Permit | 2020-09-28 | 2020-10-19 | 2 | DS | Ron Perttu | Forrest Rishel
Bigler Hall | 00-06750.00 | 202000164 |  | 0249-000 | Phase 2B Reno | Building Permit |  | 2020-02-26 | 2 | OD | Rich O'Donald |  | Steve Merrick
Biobehavioral Health | 00-07354.00 | 202001213 | 541304 | 0654-000 | Suite 230 Reno | Building Permit | 2020-12-08 | 2021-01-05 | 2 | OD | Robert Lingenfelter
Boucke | 00-07497.00 |  |  | 0013-000 | Convert Rm 325 into Single User Toilet Rooms | REJECTED |  | 2020-12-03 | 2 | DS | Ron Perttu | Scot Miller
Bryce Jordan Center | 00-06501.00 | 202000131 | 538573 | 0045-000 | Basketball Suite Reno | Building Permit |  | 2020-02-17 | 2 | OD | Marv Bevan
Bryce Jordan Center | 00-06501.00 | 202000862 |  | 0045-000 | Basketball Suite Reno - Fire Alarm | Building Permit | 2020-08-19 | 2020-09-21 | 2 | OD | Marv Bevan
Bryce Jordan Center | 00-06501.00 | 202001006 | 540623 | 0045-000 | Basketball Suite Reno - Sprinkler | Building Permit |  | 2020-10-28 | 2 | OD | Marv Bevan
Bryce Jordan Center | 00-06501.00 | 202001091 | 540845 | 0045-000 | Basketball Suite Reno Ph 2 | Building Permit |  | 2020-11-12 | 2 | OD | Marv Bevan |  | Ben B.
Bryce Jordan Center | 00-07225.00 | 202000326 |  | 0045-000 | Power Distribution Upgrades | Building Permit | 2020-03-05 | 2020-05-11 | 2 | OD | Nathan Patrick
Business Bldg | 00-07040.00 | 202000423 |  | 0023-001 | Suite 11 & 204 Reno | Building Permit | 2020-02-25 | 2020-06-08 | 2 | DS | Julie Patrick | Forrest, Bob Jenk
Business Bldg | 00-07176.00 | 202091450 | 541116 | 0023-001 | Mount Message Tickers and TVs | Building Permit | 2020-11-16 | 2020-12-21 | 1 | OD | Robert Lingenfelter | Mike Rupert
Carpenter | 00-07044.00 | 202000099 |  | 0453-000 | DNA Lab 401 & 401A Fire Alarm | C of O | 2020-01-13 | 2020-02-06 | 2 | OD | Chad Spackman
Carpenter | 00-07044.00 | 202000154 |  | 0453-000 | DNA Lab 401 & 401A Revision | C of O |  | 2020-02-24 | 2 | OD | Chad Spackman
Carpenter | 00-07044.00 | 202000381 |  | 0453-000 | DNA Lab 401 & 401A Elec Revision | C of O |  | 2020-05-27 | 2 | OD | Chad Spackman
Carpenter | 00-07044.00 | 202090942 | 540228 | 0453-000 | Rm 304 Chilled Water Modification | Building Permit | 2020-08-31 | 2020-09-22 | 1 | OD | Paul P, C Spackman
Centralized Biological Lab | 00-06730.00 | 202001109 | 540991 | 0404-000 | Cage Wash Modification - Fire Alarm | Building Permit | 2020-10-29 | 2020-12-11 | 2 | OD | J Lucas, M. vanouse
Chemistry | 00-07166.00 |  |  | 0050-000 | Helium Pipe Install | Pending | 2020-12-21 |  | 2 | DS | Matt Leah | Bryan O, Pete C.
Covered Inventory Bldg at Salvage | 00-06062.00 | 202000813 |  | 0037-007 | New Structure | Building Permit | 2020-06-29 | 2020-08-27 | 2 | DS | Ron Perttu | Dave R, Forrest R
Covid 19 Testing & Surveillance Ctr | 00-08133.00 | 202001144 | 541236 | 0998-133 | Covid 19 CLIA Facility Improvements | Building Permit | 2020-11-23 | 2020-12-11 | 2 | DS | Derek Leonard | Andy bucha
Curtin Hall | 00-06750.00 | 202000155 |  | 0248-000 | Phase 2B Reno | Building Permit |  | 2020-02-24 | 2 | OD | Rich O'Donald |  | Tom Lang
Davey Lab | 00-07214.00 | 202000356 |  | 0412-000 | Rm 334-338 Quantum Theory Ctr Reno | Building Permit | 2020-03-13 | 2020-05-21 | 2 | OD | Jason Anderson
Davey Lab | 00-07214.00 | 202000524 |  | 0412-000 | Rm 334-338 Quantum Theory Ctr Partial Occupancy | C of O |  | 2020-07-22 | 2 | OD | Jason Anderson
Deike | 00-05846.00 | 202000104 |  | 0503-000 | Basement Reno Ph2 Rock Prep | Building Permit | 2020-01-10 | 2020-02-05 | 2 | OD | David Peck
Deike | 00-06886.00 | 202000430 |  | 0503-000 | Ground Floor Offices and Museum Reno | Building Permit | 2020-03-16 | 2020-06-12 | 2 | OD | Jason Smith
Deike | 00-06886.00 | 202000809 |  | 0503-000 | Offices and Museum Additional Space Rev. | Building Permit | 2020-08-11 | 2020-08-27 | 2 | OD | Jason Smith
Dunham Hall | 00-06877.00 | 202000053 |  | 0290-002 | Fire Sprinkler System Reno | Building Permit | 2019-12-23 | 2020-01-22 | 2 | OD | Jason Anderson
Earth & Engineering Sciences | 00-06734.00 | 202000328 |  | 0035-000 | Earth& Environmental Systems Institute Suite Reno | Building Permit | 2020-03-06 | 2020-05-11 | 2 | OD | Bill Waugh
Eisenhower Auditorium | 00-06584.00 | 202000340 |  | 0011-000 | Phase 5 Upgrades | Building Permit | 2020-03-05 | 2020-05-13 | 2 | OD | Christie Holloway | R. Ligenfelter
Eisenhower Auditorium | 00-06584.00 | 202001131 | 541086 | 0011-000 | Shaft & Mechnical Rm Revision | Building Permit |  | 2020-12-08 | 2 | OD | Christie Holloway | R. Ligenfelter
Eisenhower Chapel | 00-06381.00 | 202090625 |  | 0006-000 | Roof Replacement | Building Permit | 2020-06-17 | 2020-08-03 | 1 | DS | Christie Holloway | Dan Aumiller
Electrical Engineering East | 00-07353.00 |  |  | 0315-000 | RM 16 ALD Equipment Upgrades | Pending | 2020-12-21 |  | 2 | DS | Dwayne Rush | Bryan Ondrasik
Electrical Engineering West | 00-07399.00 | 202000755 |  | 0302-000 | Rm 113L Infrastructure for Dilution Refridgerator | Building Permit | 2020-07-01 | 2020-08-18 | 2 | DS | Julie Patrick | Scot M, Bryan O
Electrical Engineering West | 00-07296.00 | 202001157 | 541137 | 0302-000 | Room 6 Reno | Building Permit | 2020-11-23 | 2020-12-09 | 2 | OD | Brian Hayes
Field Hockey Stadium | 00-06964.00 | 202000493 |  | 0848-000 | New Field Hockey Stadium | Building Permit | 2020-04-29 | 2020-07-06 | 2 | OD | Marv Bevan
Food Sciences | 00-06095.00 | 202000001 |  | 0107-001 | Silo Pit Safety Improvements | Building Permit | 2019-12-12 | 2020-01-07 | 2 | DS | Morgan VanOuse | Kathy Poissant
Food Sciences | 00-06970.00 | 202000148 |  | 0107-001 | Rm 417 Washer/Dryer Install | Building Permit | 2020-01-28 | 2020-02-21 | 2 | OD | Mike Hoffman
Fox Hollow Bldg | 00-06950.00 | 202090552 |  | 0193-005 | Lintel Install for Exterior Doors | Building Permit | 2020-05-18 | 2020-07-16 | 1 | DS | Ron Perttu | Andy Bucha
Fox Hollow Bldg | 00-06950.00 | 202000578 |  | 0193-005 | Carpenter & Paint Shop Relocation | Building Permit | 2020-06-12 | 2020-07-21 | 2 | DS | Ron Perttu | Andy Bucha
Fox Hollow Bldg | 00-06950.00 | 20210008 | 541108 | 0193-005 | Carpenter & Paint Shop Relocation Electrical Revision | Pending | 2020-11-16 | 2021-01-07 | 2 | DS | Ron Perttu | Pete Caporuscio
Fox Hollow Bldg | WO#H226165 | 202091515 | 541322 | 0193-005 | Rm 112A Electrical circuit for washing machine | Building Permit | 2020-12-09 | 2021-01-05 | 1 | DS | Ducan Spence | Walter Godissart
Garban Hall | 00-06877.00 | 202000052 |  | 0290-002 | Fire Sprinkler System Reno | Building Permit | 2019-12-23 | 2020-01-22 | 2 | OD | Jason Anderson
Greenberg - Morgan Academic Center | 00-07277.00 | 202090665 |  | 0835-000 | Accessible Paths to Greenberg Complex | Building Permit | 2020-07-01 | 2020-08-21 | 1 | DS | Marv Bevan | Mike R, Jason M.
Grubb Hall | 00-06877.00 | 202000051 |  | 0290-002 | Fire Sprinkler System Reno | Building Permit | 2019-12-23 | 2020-01-22 | 2 | OD | Jason Anderson
Hallowell | 00-06955.00 | 202000032 |  | 0317-000 | Suite 305 Ancient DNA Lab | Building Permit | 2019-12-20 | 2020-01-16 | 2 | OD | Chad Spackman |  | Ben Bidelspach
Hallowell | 00-06955.00 | 202000725 |  | 0317-000 | Suite 305 Ancient DNA Lab Fire Alarm | Building Permit | 2020-07-14 | 2020-08-21 | 2 | OD | Chad Spackman
Hallowell | 00-06756.00 | 202000147 |  | 0317-000 | Chilled Water Project | Building Permit | 2020-01-28 | 2020-02-21 | 2 | OD | Alan Zimmerman
Hallowell | 00-06756.00 | 202000838 |  | 0317-000 | Chilled Water Project - Modification | Building Permit |  | 2020-09-02 | 2 | OD | Alan Zimmerman
Hallowell | 00-07226.00 | 202000579 |  | 0317-000 | Create Student Commons in Rms 110-112 | Building Permit | 2020-06-11 | 2020-07-28 | 2 | OD | Dwayne Rush
Hamilton Hall | 00-07111.00 | 202000263 |  | 0205-000 | Bathroom Reno Ph 2 | CANCELLED | 2020-02-14 | 2020-04-28 | 2 | OD | Rich O'Donald
Henning Replacement Bldg | 00-05321.00 | 202000097 |  | 0119-000 | Updated Foundation - cancelled by 202000161 | CANCELLED |  | 2020-02-06 | 2 | OD | Jeff Spackman
Henning Replacement Bldg | 00-05321.00 | 202000161 |  | 0119-000 | Updated Foundation - Second Revision | Building Permit | 2020-02-05 | 2020-03-03 | 2 | OD | Jeff Spackman
Henning Replacement Bldg | 00-05321.00 | 202000417 |  | 0119-000 | Animal, Veterinary & Biomedical - New Building | Building Permit | 2020-02-05 | 2020-06-08 | 2 | OD | Jeff Spackman
Holmes Hall | 00-06053.00 | 202090056 |  | 0212-000 | Domestic Hot Water Plumbing Upgrades | Building Permit | 2020-01-10 | 2020-01-28 | 1 | OD | Matt Vail
Horse Barn | 00-05615.00 |  |  | 0183-028 | Older Horse Barn Addition | CANCELLED | 2020-01-21 |  | 1 | DS | Morgan VanOuse | Mike Rupert
Horse Barn | 00-05615.00 | 202090941 | 540271 | 0126-001 | Horse Exerciser | Building Permit | 2020-09-04 | 2020-10-01 | 1 | DS | Morgan VanOuse | Mike Rupert
HUB | 00-06991.00 | 202000925 | 540234 | 0005-000 | AT&T Distributed Antenna System | Building Permit |  | 2020-09-28 | 2 | OD | Jason Anderson
Indoor Multisport | 00-07405.00 | 202090667 |  | 0846-000 | Accessible Pathways | Building Permit | 2020-07-06 | 2020-08-21 | 1 | DS | Kurt Coduti | Jason McCoy
Intramural | 00-07219.00 | 202000270 |  | 0804-000 | Shake Smart Fitout | C of O | 2020-02-18 | 2020-04-28 | 2 | OD | Matt Vail
Intramural | 00-06990.00 | 202000926 | 540235 | 0804-000 | AT&T Distributed Antenna System | Building Permit |  | 2020-09-28 | 2 | OD | Jason Anderson
Johnston Commons & Tunnels | 00-06168.00 | 202000543 |  | 0276-000 | Ph 2A Interim ME Plant/ Heat Exchanger Revision | Building Permit | 2020-06-04 | 2020-07-17 | 2 | OD | Rich O'Donald
Katz | 00-06809.00 | 202000761 |  | 0991-200 | Accessibility Upgrades | Building Permit | 2020-07-17 | 2020-08-18 | 2 | OD | Dwayne Rush
Kern | 00-03448.00 | 202000331 |  | 0452-000 | Graduate School Suite 111 Partial Occupancy | C of O | 2020-03-02 | 2020-04-29 | 2 | OD | Jason Smith |  | Ben
Lasch Outdoor Practice Field | 00-06878.00 | 202000371 |  | 0995-108 | Practice Field Reno | Building Permit |  | 2020-05-27 | 2 | OD | Marv Bevan
Lasch | 00-06019.00 | 202000477 |  | 0845-000 | Quarter Back Positions Room | Building Permit |  | 2020-06-29 | 2 | OD | Marv Bevan
Leete Hall | 00-06053.00 | 202090055 |  | 0213-000 | Domestic Hot Water Plumbing Upgrades | Building Permit | 2020-01-10 | 2020-01-28 | 1 | OD | Matt Vail
Leonhard | 00-06934.00 | 202000398 |  | 0319-000 | Knowledge Commons | Building Permit | 2020-03-26 | 2020-06-05 | 2 | OD | Brian Hayes
Leonhard | 00-06934.00 |  |  | 0319-000 | Knowledge Commons - Sprinkler | Pending | 2020-11-23 |  | 2 | OD | B Hayes, T Scanlan
Material Research Institute | 00-06012.05 |  |  | 0965-002 | Lab 128 Reno | Rejected | 2020-01-24 | 2020-02-17 | 2 | OD | Morgan VanOuse
Material Research Institute | 00-06012.05 |  |  | 0965-002 | Lab 128 Reno | Rejected |  | 2020-06-29 | 2 | OD | Morgan VanOuse
Material Research Institute | 00-06012.05 | 202000544 |  | 0965-002 | Lab 128 Reno - Robotic Laser | Building Permit |  | 2020-07-16 | 2 | OD | Morgan VanOuse
Material Research Institute | N/A | 202000307 |  | 0965-002 | Rm 122 & 124 EB60 Install | Building Permit | 2020-03-02 | 2020-05-01 | 2 | OD | Spackman VanOuse
Mueller | 00-07112.00 | 202000016 |  | 0409-000 | 217B Office Reno | C of O | 2019-12-11 | 2020-01-10 | 2 | OD | Jason Anderson |  | Tom Lang
Nittany Apartments Bldg 21 | 00-07457.00 | 202091451 | 541070 | 0215-021 | Relocation of Electrical Panel | Building Permit | 2020-11-17 | 2020-12-21 | 1 | OD | Matt Vail, Maria M.
Nittany Apartments Bldg 35 | 00-07457.00 | 202091452 | 541071 | 0215-035 | Relocation of Electrical Panel | Building Permit | 2020-11-17 | 2020-12-21 | 1 | OD | Matt Vail, Maria M.
North Campus Chiller Bldg | 00-06044.00 | 202000422 |  | 0910-004 | Fire Pump Room Modifications | Building Permit | 4/44/20 | 2020-06-08 | 2 | OD | Nate Patrick |  | Mike Kulbacki
Oaks (formerly Exec Ed) | 00-06411.00 | 202000071 |  | 0019-000 | Remodeling of Building | Building Permit |  | 2020-01-30 | 2 | OD | Matt Leah
Oaks (Marriot & Exec ED Bldg) | 00-06411.00 | 202000438 |  | 0019-000 | Building Remodel - Fire Alarm | Building Permit |  | 2020-06-16 | 2 | OD | Matt Leah
Oaks (Marriot & Exec ED Bldg) | 00-06411.00 | 202000486 |  | 0019-000 | Building Remodel - Sprinkler | Building Permit |  | 2020-07-06 | 2 | OD | Matt Leah
Packer Hall | 00-06750.00 | 202000162 |  | 0247-000 | Phase 2B Reno | Building Permit |  | 2020-02-24 | 2 | OD | Rich O'Donald |  | Steve Merrick
Pattee | 00-06987.00 | 202000924 | 540233 | 0003-000 | AT&T Distributed Antenna System | Building Permit |  | 2020-09-28 | 2 | OD | Jason Anderson
Patterson Hall | 00-06877.00 | 202000054 |  | 0290-002 | Fire Sprinkler System Reno | Building Permit | 2019-12-23 | 2020-01-22 | 2 | OD | Jason Anderson
Physical Plant (OPP) | G912774 |  |  | 0904-000 | Rm 121A Humidifier Install | Rejected | 2020-02-21 | 2020-05-01 | 1 | DS |  | Bryan Ondrasik
Physical Plant (OPP) | G912774 | 202000500 |  | 0904-000 | Rm 121A Humidifier Install | Building Permit | 2020-05-13 | 2020-07-07 | 2 | DS | Chester Fletcher Jr. | Bryan Ondrasik
Pond Lab | 00-06691.00 | 202000030 |  | 0403-000 | Steam to Hot Water Conversion | Building Permit | 2019-12-19 | 2020-01-14 | 2 | DS | Derek Leonard | Adam Davis | Ben Bidelspach
Pond Lab | 00-07139.00 |  |  | 0403-000 | Steam to Hot Water Conversion Ph 2 | Pending | 2020-12-15 |  | 2 | DS | Derek Leonard | Ting Zhou
Reber | 00-07180.00 | 202000335 |  | 0303-000 | Lab 108 & 109 Reno | Building Permit | 2020-03-12 | 2020-05-11 | 2 | DS | Bill Waugh | Forrest R. Bryan O.
Reber | 00-06856.00 | 202000353 |  | 0303-000 | Lower Level Instructional Suite | Building Permit | 2020-03-13 | 2020-05-18 | 2 | OD | Bill Waugh
Reber | 00-06856.00 | 202001130 | 541051 | 0303-000 | Lower Level Instructional Suite - Sprinkler | Building Permit |  | 2020-12-11 | 2 | OD |  | Dave Reisinger
Research Bldg East | 00-07254.00 | 202000201 |  | 0028-000 | Workroom 127 Reno | Building Permit | 2020-02-06 | 2020-03-09 | 2 | OD | Brian Hayes
Research Bldg East | 00-06735.00 | 202000724 | 539783 | 0028-000 | Lab 218 - Sprinkler | Building Permit |  | 2020-09-21 | 2 | OD | Brian Hayes
Research Bldg East | 00-06735.00 | 202000844 | 540075 | 0028-000 | Lab 218 - Fire Alarm | Building Permit |  | 2020-09-21 | 2 | OD | Brian Hayes
Research Bldg West | 00-07017.00 | 202000034 |  | 0271-000 | Lab 113 A & B Reno | Building Permit | 2019-12-20 | 2020-01-21 | 2 | OD | Brian Hayes |  | Tom Lang
Research Bldg West | 00-07261.00 | 202000441 |  | 0271-000 | Lab 14A Reno | Building Permit | 2020-03-27 | 2020-06-16 | 2 | OD | Dwayne Rush
Research Bldg West | 00-07222.00 | 202000789 |  | 0271-000 | LAB 111 Ventilation Reno | Building Permit | 2020-08-03 | 2020-09-02 | 2 | DS | Brian Hayes | Helen, Bob Z Scot M
Research Bldg West | 00-07505.00 | 202001154 | 541151 | 0271-000 | Rm 121 HVAC Reno | Building Permit |  | 2020-12-21 | 2 | OD | Bill Waugh
Research & Teaching Space 2 (West 2) | 00-06895.00 | 202000709 |  | 0312-000 | New Structure | Building Permit | 2020-06-09 | 2020-07-30 | 2 | OD | Brian Hayes
Rider Bldg | 00-07101.00 | 202000369 |  | 0998-072 | Suite 507 Renovations | Building Permit | 2020-03-23 | 2020-05-21 | 2 | OD | Marv Bevan
Rider Bldg | 00-07101.00 | 202000845 |  | 0998-072 | Suite 507 Revisions | Building Permit | 2020-08-19 | 2020-09-04 | 2 | OD | Marv Bevan
Robinson Hall | 00-06053.00 | 202090059 |  | 0214-200 | Domestic Hot Water Plumbing Upgrades | Building Permit | 2020-01-10 | 2020-01-28 | 1 | OD | Matt Vail
Runkle Hall | 00-06053.00 | 202090058 |  | 0214-000 | Domestic Hot Water Plumbing Upgrades | Building Permit | 2020-01-10 | 2020-01-28 | 1 | OD | Matt Vail
Salvage Warehouse | 00-06062.00 | 202000814 |  | 0925-000 | Loading Dock Addition | Building Permit | 2020-06-29 | 2020-08-27 | 2 | DS | Ron Perttu | Dave R, Forrest R
Salvage Warehouse | 00-06062.00 | 202000824 |  | 0925-000 | Loading Dock Addition - Fire Alarm | Building Permit |  | 2020-08-31 | 2 | OD | Ron Perttu
Science Park Annex Library | 00-04862.00 |  |  | 0999-022 | Exhaust Fan Install | REJECTED | 2020-03-12 | 2020-05-29 | 1 | DS |  | Bob Z. Helen
Science Park Annex Library | 00-04862.00 | 202000754 |  | 0999-022 | Quarantine Book Area Exhaust Fan | Building Permit | 2020-07-20 | 2020-08-18 | 2 | DS | Chad Spackman | Helen Bob Bryan O
Shields | 00-06802.00 | 202001093 | 540871 | 0004-000 | 1st & 3rd Flr Reno | Building Permit |  | 2020-11-12 | 2 | OD | Chad Spackman
Smith Bldg 1 | 00-07250.00 | 202091329 | 540861 | 0999-501 | Cupola Removal | Building Permit | 2020-10-22 | 2020-11-25 | 1 | DS |  | Mike Rupert
Steam Services | 00-07270.00 | 202000302 |  | 0911-007 | Area 3 Shop | Building Permit | 2020-02-27 | 2020-05-07 | 2 | OD | Dwayne Rush | Andy Bucha
Steam Services | 00-07270.00 | 202000680 |  | 0911-007 | Area 3 Shop - Sprinkler | Building Permit |  | 2020-08-07 | 2 | OD | Dwayne Rush
Student Health Ctr | 00-07529.00 | 202090551 |  | 0053-000 | Corridor door install | C of O | 2020-06-19 | 2020-07-16 | 2 | DS | Derek Leonard | Kathy Poissant
Student Health Ctr | 00-07529.00 | 202000707 |  | 0053-000 | Fourth Floor Negative Pressure Rooms | C of O | 2020-07-29 | 2020-08-04 | 2 | DS | Derek Leonard | Kathy Poissant
Test Track Office | 00-05194.00 | 202000297 |  | 0196-002 | Domestic Water Mods | Building Permit | 2020-02-27 | 2020-05-07 | 2 | OD | Jeff Spackman
Test Track Garage(Vehicle Test Lab) | 00-05194.00 | 202000298 |  | 0196-005 | Domestic Water Mods | Building Permit | 2020-02-27 | 2020-05-07 | 2 | OD | Jeff Spackman
Wagner | 00-05183.00 | 202000365 |  | 0014-000 | Indoor Rifle Range Reno | Building Permit | 2020-03-13 | 2020-05-27 | 2 | OD | Ron Perttu
Walker | 00-05610.00 | 202000316 |  | 0504-000 | Ph 2 HVAC Reno | Building Permit | 2020-02-24 | 2020-05-07 | 2 | OD | Alan Zimmerman
Walker | 00-05610.00 | 202000788 |  | 0504-000 | Ph 2 Hvac Reno - Partial Occupancy | C of O | 2020-08-11 | 2020-08-25 | 2 | OD | Alan Zimmerman
Walker | 00-06298.00 | 202000749 |  | 0504-000 | ADA Upgrades to Various Restrooms | Building Permit | 2020-07-16 | 2020-08-13 | 2 | DS | Ron Perttu | Forrest R, Kathy P.
Warnock Commons | 00-06053.00 | 202000028 |  | 0274-000 | Mechanical Room Reno | Building Permit | 2019-12-17 | 2020-01-14 | 2 | OD | Matt Vail |  | Ben Bidelspach
Warnock Commons | 00-06053.00 | 202000485 |  | 0274-000 | Mechanical Room Reno - Fire Alarm | Building Permit | 2020-05-08 | 2020-07-06 | 2 | OD | Matt Vail
Warnock Commons | 00--07360.00 | 202000531 |  | 0274-000 | Blue Spoon Grill - Service Line Reno | Building Permit | 2020-05-30 | 2020-07-17 | 2 | OD | Matt Vail
West Campus Chiller Bldg | 00-06919.00 | 202000609 |  | 0943-000 | 3000 Ton Expansion | Building Permit |  | 2020-07-30 | 2 | OD | Nate Patrick
West Campus Parking Deck | 00-05940.00 | 202001061 | 540626 | 0995-086 | New Structure - Sprinkler | Building Permit |  | 2020-11-02 | 2 | OD | Kurt Coduti
West Campus Steam Plant (Power Plt) | 00-04966.00 | 202000010 |  | 0911-000 | Heat and Power Expansion | Building Permit |  | 2020-01-07 | 2 | OD | Jeff Spackman |  | Ben
West Campus Steam Plant (Power Plt) |  | 202000302 |  | 0911-000 | C of O only | C of O |  | 2020-04-22 | 2 | OD
West Campus Steam Plant (Power Plt) |  | 202000680 |  | 0911-000 | C of O only | C of O |  | 2020-07-29 | 2 | OD
West Campus Substation | 00-04966.00 | 202000002 |  | 0906-003 | Replacement Structure | Building Permit |  | 2020-01-07 | 2 | OD | Jeff Spackman |  | Ben
Westgate | 00-07321.00 | 202090157 |  | 0039-000 | W336 Partition | Building Permit | 2020-01-22 | 2020-03-09 | 1 | DS | Dwayne Rush | Mike Rupert
White | 00-07219.00 | 202000552 |  | 0802-000 | Shake Smart Fitout | C of O | 2020-05-29 | 2020-07-20 | 2 | OD | Matt Vail
Willard | 00-05743.00 |  |  | 0012-000 | Foundation to Grade Reno - Fire Alarm | REJECTED |  | 2020-06-29 | 2 | OD | Monica Reed
Willard | 00-05743.00 | 202000772 |  | 0012-000 | Foundation to Grade Reno - Fire Alarm | Building Permit |  | 2019-08-20 | 2 | OD | Monica Reed
WWTP Sewage Pumping Station | 00-05991.00 | 202000914 | 540137 | 0994-028 | Building Renovation | Building Permit |  | 2020-09-24 | 2 | OD | Dave Peck
WWTP Primary Settling Influent EQ | 00-05991.00 | 202000915 | 540183 | 0994-028 | Building Renovation | Building Permit |  | 2020-09-24 | 2 | OD | Dave Peck |  | Ben
WWTP EPS Electrical Bldg | 00-05991.00 | 202000916 | 540184 | 0994-068 | New Structure | Building Permit |  | 2020-09-24 | 2 | OD | Dave Peck
WWTP MBR Facility | 00-05991.00 | 202000966 | 540424 | 0994-066 | New Structure - Sprinkler | Building Permit |  | 2020-10-29 | 2 | OD | Dave Peck |  | Ben
WWTP Headworks PTF | 00-05991.00 | 202000968 | 540423 | 0994-065 | New Structure - Sprinkler | Building Permit |  | 2020-10-29 | 2 | OD | Dave Peck |  | Ben

## Commonwealth
CAMPUS 2020 | PSU PROJECT # | Permit # |  | BLDG. # | DESCRIPTION | STATUS | DATE SENT | DATE RETURNED | PERMIT LEVEL | DS/OD
ABINGTON CAMPUS 0979-000
Woodland | 00-06496.00 | 202000004 |  | 0979-008 | Classroom 132 Reno HVAC Revision | Building Permit | 2019-12-10 | 2020-01-07 | 2 | OD
ALTOONA CAMPUS 0974-000
Cedar Hall | 00-06905.00 |  |  | 0974-003 | HVAC Upgrades Ph 2 | Pending | 2020-10-29 |  | 2 | OD | Keister, McNutt
Oak Hall | 00-07141.00 | 202090306 |  | 0974-004 | Exterior Patio Rehabilitation | Building Permit | 2020-03-06 | 2020-05-27 | 1 | OD
Spruce Hall | 00-07378.00 |  |  | 0974-012 | Office Space Reno | REJECTED | 2020-03-26 | 2020-05-29 | 1 | OD | Justin Keister
BEAVER CAMPUS 0986-000
Gymnasium | 00-06837.00 | 2020090766 |  | 0986-009 | Roof Replacement | Building Permit | 2020-07-15 | 2020-09-04 | 1 | OD | Hollick
Gymnasium | 00-06837.00 | 202000928 | 539846 | 0986-009 | Roof Fall Protection | Building Permit | 2020-09-15 | 2020-09-28 | 2 | OD | Hollick
BEHREND CAMPUS 0972-000
AMIC Lab | 00-07404.00 | 202000431 |  | 0972-181 | Lab 258 Reno for MWRI Teaching Lab | Building Permit | 2020-04-23 | 2020-06-12 | 2 | OD
Fasenmyer | 00-07042.00 | 202000765 |  | 0972-080 | Swing Space | Building Permit | 2020-07-14 | 2020-08-19 | 2 | OD
Federal House | 00-07049.00 | 202001017 | 540466 | 0972-071 | Building Reno and Addition | Building Permit |  | 2020-10-22 | 2 | OD | Marcus Marasco
Glenhill Farmhouse | 00-03258.00 | 202000510 |  | 0972-001 | HVAC Upgrades | Building Permit |  | 2020-07-10 | 2 | OD
Knowledge Park Bldg 3 | N/A | 202000795 |  | 0972-000 | Project Matchbox | Building Permit |  | 2020-08-31 | 2 | OD | Chuck Peters
Knowledge Park Bldg 4 |  | 202001010 | 540621 | 0972-000 | Cyient Tenant Fit-out | Building Permit |  | 2020-10-19 | 2 | OD | Chuck Peters
Lilley Library | 00-07130.00 | 202000275 |  | 0972-030 | Ground Flr Elec and Data Cabling | C of O |  | 2020-04-28 | 2 | OD | Marcus Marasco
Science Building | 00-06846.00 | 202000338 |  | 0972-011 | Roof Fall Protection | Building Permit | 2020-03-09 | 2020-05-13 | 2 | OD
Science Building | N/A | 202090299 |  | 0972-011 | Roof Replacement | Building Permit | 2020-03-02 |  | 1 | OD
Science Building | 00-07403.00 |  |  | 0972-011 | Lab 126 Reno | Rejected | 2020-04-23 | 2020-06-16 | 2 | OD | Marcus Marasco
Science Building | 00-07403.00 | 202000568 |  | 0972-011 | Lab 126 Reno | Building Permit |  | 2020-07-22 | 2 | OD | Marcus Marasco
BERKS CAMPUS 0980-000
Beaver Community Center | 00-06497.00 |  |  | 0980-002 | East Addition | Rejected | 2019-12-20 | 2020-01-20 | 2 | OD | Kyle Hollick
Beaver Community Center | 00-06497.00 | 202000309 |  | 0980-002 | East Side Addition | Building Permit | 2020-02-03 | 2020-06-05 | 2 | OD | kyle Hollick
Beaver Community Center | 00-06497.00 | 202000308 |  | 0980-002 | West Side Addition | Building Permit | 2020-02-03 | 2020-06-05 | 2 | OD | kyle Hollick
Beaver Community Center | 00-06497.00 | 202000311 |  | 0980-002 | Building Renovation | Building Permit | 2020-02-03 | 2020-06-05 | 2 | OD | kyle Hollick
Beaver Community Center | 00-06497.00 |  |  | 0980-002 | Temporary Showers | Pending | 2020-05-20 |  | 2 | OD | Kyle Hollick
Bowman Resident Center | 00-06863.00 | 202000341 |  | 0980-000 | HVAC Upgrades | CANCELLED |  | 2020-05-12 | 2 | OD | Neal McNutt
Franco | 00-07184.00 | 202090305 |  | 0980-001 | Façade Flashing Repairs | Building Permit | 2020-03-06 | 2020-05-27 | 1 | OD
Luerssen | 00-07186.00 | 202000832 |  | 0980-004 | Stair Tower Door Replacement | Building Permit | 2020-08-13 | 2020-08-31 | 2 | OD | Hollick, Ritter
Perkins Student Ctr | 00-06497.00 | 202000310 |  | 0980-005 | North Addition and Bridge | Building Permit | 2020-02-03 | 2020-06-05 | 2 | OD | Kyle Hollick
Perkins Student Ctr | 00-06497.00 | 202001149 | 541039 | 0980-005 | North Addition and Bridge - Sprinkler | Building Permit |  | 2020-12-11 | 2 | OD | Kyle Hollick
Walkways | 00-06497.00 | 202000848 |  | 0980-000 | ADA Walkways | Building Permit |  | 2020-09-05 | 2 | OD | Kyle Hollick
BRANDYWINE CAMPUS 0989-000
Commons Athletic Center | 00-07521.00 | 202001068 | 540869 | 0989-005 | Police Suite Upgrades | Building Permit | 2020-10-19 | 2020-11-12 | 2 | DS | Andy Ritter | Andy Bucha
CAPITAL CAMPUS 0985-000
Nittany Village Bldg A | 00-06741.00 | 202000007 |  | 0985-110 | Fire Alarm Upgrades | C of O | 2019-12-13 | 2020-01-03 | 2 | OD | keister
Nittany Village Bldg A | 00-06741.00 | 202000817 |  | 0985-110 | Laundry Room Reno | Building Permit | 2020-07-23 | 2020-09-02 | 2 | OD | Keister
Nittany Village Bldg B | 00-06741.00 | 202000008 |  | 0985-111 | Fire Alarm Upgrades | C of O | 2019-12-13 | 2020-01-03 | 2 | OD | keister
Nittany Village Bldg A | 00-06741.00 | 202000816 |  | 0985-110 | Laundry Room Reno | Building Permit | 2020-07-23 | 2020-09-02 | 2 | OD | Keister
Nittany Village Bldg C | 00-06741.00 | 202000009 |  | 0985-112 | Fire Alarm Upgrades | C of O | 2019-12-13 | 2020-01-03 | 2 | OD | keister
Olmsted | 00-07146.00 | 202090218 |  | 0985-001 | Cooling Tower Roof Replacement | C of C | 2020-02-06 | 2020-03-18 | 1 | OD | John Krause
Olmsted | 00-07259.00 |  |  | 0985-001 | Stacks Market Place Serviing Line Reno | Rejected | 2020-09-23 |  | 2 | OD | wenger Krause
Olmsted | 00-07259.00 | 202001019 | 540662 | 0985-001 | Stacks Market Place Serviing Line Resubmission | Building Permit | 2020-10-06 | 2020-10-22 | 2 | OD | Wenger, Krause
Paxton House | 00-06822.00 | 202090217 |  | 0985-100 | Roof Replacement - Resubmission | Building Permit | 2020-02-07 | 2020-03-18 | 1 | OD | Neil McNutt
Smart Home | 00-07221.00 | 202090308 |  | 0985-106 | Roof Replacement | C of C | 2020-03-05 | 2020-05-27 | 1 | OD
DICKINSON SCHOOL OF LAW-CARLISLE 0991-000
Trickett Hall | 00-06445.00 | 202000187 |  | 0991-001 | Clock Tower Rehab | Building Permit | 2/3/20250 | 2020-03-03 | 2 | OD
DUBOIS CAMPUS 0976-000
Hiller | 00-07322.00 | 202000997 | 540478 | 0976-002 | Police Office Reno | Building Permit |  | 2020-10-19 | 2 | OD | D. Wenger/D. Parmalee
FAYETTE CAMPUS 0984-000
Biomed | 00-06833.00 | 202000592 |  | 0984-008 | Common Corridor Interior Finish Reno | Building Permit |  | 2020-07-30 | 2 | OD | Kobelenske, M. Marasco
Eberly | 00-07192.00 | 202000396 |  | 0984-001 | RTUs Replacement | Building Permit |  | 2020-06-09 | 2 | OD
Eberly | 00-07357.00 | 202001129 | 541052 | 0984-001 | Police & Public Safety Offices Reno | Building Permit |  | 2020-12-08 | 2 | OD | Marcus Marasco
FRUIT RESEARCH CENTER 0968-000
FREC Pole Building | 00-06477.00 | 202000176 |  | 0968-003 | New Structure Resubmission | Building Permit | 2020-01-28 | 2020-02-26 | 2 | OD
GRAPE RESEARCH 0967-000
Pole Barn | 00-07305.00 |  |  | 0967-009 | Electrical Upgrades | Pending | 2020-10-29 |  | 1 | DS | Justin Keister
GREAT VALLEY 0993-000
Safeguard Scientific | 00-05224.00 |  |  | 0993-004 | Pathway and Pollinator Garden | Rejected | 2020-06-24 | 2020-08-13 | 1 | OD | hollick, Ritter
GREATER ALLEGHENY CAMPUS 0978-000
Frable | 00-07224.00 | 202090550 |  | 0978-004 | 2nd Floor Reno | Building Permit | 2020-05-18 | 2020-07-16 | 1 | OD
Ostermayer Lab | 00-06375.00 | 202000158 |  | 0978-012 | Building Reno | Building Permit |  | 2020-02-24 | 2 | OD
HAZELTON CAMPUS 0973-000
High Acres Café | 00-05591.00 | 202090159 |  | 0973-010 | Building Envelope Rehab | Building Permit | 2020-02-02 | 2020-03-11 | 1 | OD
Slusser-Bayzick | 00-06655.00 | 202090309 |  | 0973-007 | Roof Replacement | Building Permit | 2020-03-05 | 2020-05-27 | 1 | OD
Slusser-Bayzick | 00-06655.00 | 202000793 |  | 0973-007 | Roof Fall Protection | Building Permit |  | 2020-08-31 | 2 | OD | Parmelee, Hollick
HERSHEY 0990-000
Chapel |  |  |  | 0990-000 | New Addition | Cancelled | 2020-08-25 |  | 2 | OD
LEHIGH VALLEY 0977-000
Maintenance Bldg | 00-06000.00 | 202000555 |  | 0977-200 | New Structure | Building Permit | 2020-05-26 | 2020-07-16 | 2 | OD | Hollick
Lehigh Valley Bldg | 00-05264.00 | 202001067 | 540841 | 0977-100 | Dining Addition - sprinkler | Building Permit |  | 2020-11-12 | 2 | OD | Ritter
MONT ALTO CAMPUS 0970-000
Allied Health Bldg | 00-06654.00 | 202000514 |  | 0971-079 | New Structure | Building Permit | 2020-05-01 | 2020-07-10 | 2 | OD | Doug Wenger
Arboretum | 0-05397.00 | 202000444 |  | 0971-034 | Arboretum Garden Phase 1 | Building Permit | 2020-04-08 | 2020-06-16 | 2 | OD
Conklin Hall | 00-07235.00 | 202000280 |  | 0971-002 | Boiler Replacement | C of O | 2020-02-13 | 2020-04-28 | 2 | OD | Doug W & John K
Conklin Hall | 00-06139.00 | 202090356 |  | 0971-002 | Roof Replacement | Building Permit | 2020-03-18 | 2020-05-29 | 1 | OD | John Krause
General Studies | 00-05927.00 | 202000180 |  | 0971-001 | Auditorium Reno | Building Permit |  | 2020-03-03 | 2 | OD
Science & Technology | 00-06654.00 | 202000513 |  | 0971-008 | Allied Health Building Addition | Building Permit | 2020-05-01 | 2020-07-10 | 2 | OD
NAVY YARD
NEW KENSINGTON 0981-000
Administration | 00-00777.00 | 202000141 |  | 0981-005 | Fire Alarm Upgrades | Building Permit |  | 2020-02-24 | 2 | OD
Arbuckle Tech | 00-00777.00 | 202000144 |  | 0981-009 | Fire Alarm Upgrades | Building Permit |  | 2020-02-24 | 2 | OD
Athletic Ctr | 00-00777.00 | 202000142 |  | 0981-006 | Fire Alarm Upgrades | Building Permit |  | 2020-02-24 | 2 | OD
Blissel Library | 00-00777.00 | 202000139 |  | 0981-003 | Fire Alarm Upgrades | Building Permit |  | 2020-02-24 | 2 | OD
Conference Ctr | 00-00777.00 | 202000145 |  | 0981-010 | Fire Alarm Upgrades | Building Permit |  | 2020-02-24 | 2 | OD
Engineering | 00-00777.00 | 202000138 |  | 0981-002 | Fire Alarm Upgrades | Building Permit |  | 2020-02-24 | 2 | OD
Engineering | 00-06164.00 | 202000410 |  | 0981-002 | Abatement Restoration | Building Permit |  | 2020-06-05 | 2 | OD
Engineering | 00-07191.00 | 202000492 |  | 0981-002 | Electronics Lab 8 Reno | Building Permit |  | 2020-07-06 | 2 | OD
Science | 00-00777.00 | 202000137 |  | 0981-001 | Fire Alarm Upgrades | Building Permit |  | 2020-02-24 | 2 | OD
Student Union | 00-04209.00 | 202000036 |  | 0981-007 | Roof Fall Protection | Building Permit | 2019-12-13 | 2020-01-20 | 2 | OD
Student Union | 00-04209.00 | 202090060 |  | 0981-007 | Roof Replacement | Building Permit | 2019-12-13 | 2020-01-28 | 1 | OD
Student Union | 00-00777.00 | 202000143 |  | 0981-007 | Fire Alarm Upgrades | Building Permit |  | 2020-02-24 | 2 | OD
Theatre | 00-00777.00 | 202000140 |  | 0981-004 | Fire Alarm Upgrades | Building Permit |  | 2020-02-24 | 2 | OD
ROCK SPRINGS 0959-000
SCHUYLKILL CAMPUS 0975-000
Administration Bldg | 00-04876.00 | 202000589 |  | 0975-006 | Addition of Elevator | Building Permit | 2020-06-04 | 2020-07-28 | 2 | OD | Hollick
Classroom Bldg | 00-06598.00 | 202000186 |  | 0975-005 | Lab Renovations | Building Permit | 2020-02-03 | 2020-03-03 | 2 | OD
Classroom Bldg | 00-06598.00 | 202000566 |  | 0975-005 | Lab Renovations Sprinkler | Building Permit |  | 2020-07-22 | 2 | OD | Hollick
Classroom Bldg | 00-06598.00 | 202000742 |  | 0975-005 | Rms 111, 111A, 111B and Mens Rm Partial Occup | Building Permit | 2020-07-24 | 2020-08-21 | 2 | OD | Hollick, Ritter
Classroom Bldg | 00-06598.00 | 202000716 |  | 0975-005 | Lab Reno - Fire Alarm | Building Permit |  | 2020-08-19 | 2 | OD | Hollick, Ritter
Classroom Bldg | 00-06598.00 | 202001172 | 541038 | 0975-005 | Lab Reno - Electrical Revision | Building Permit |  | 2021-01-07 | 2 | OD
Health & Wellness | N/A |  |  | 0975-001 | Ice Machine | Pending | 2019-12-12 |  | 1 | OD
SHAVERS CREEK 0960-000
SHENANGO CAMPUS
Forker Lab | 00-06910.00 | 202000465 |  | 0987-001 | Renovations | Building Permit | 2020-04-30 | 2020-06-29 | 2 | OD
WARMINSTER 0998-000
WILKES-BARRE CAMPUS 0983-000
Bell Science Ctr | 00-07056.00 | 202000252 |  | 0983-010 | Chiller Replacement | Building Permit | 2020-02-21 | 2020-04-28 | 2 | OD | Andy Ritter
Bell Science Ctr | 00-06186.00 | 202090607 |  | 0983-010 | Site Lighting | Building Permit | 2020-05-29 | 2020-08-03 | 1 | OD | Hollick, Parmelee
Bell Science Ctr | 00-07473.00 | 202090944 | 540165 | 0983-010 | RM T-18 Renovations | Building Permit | 2020-08-21 | 2020-10-13 | 1 | OD | D. parmelee, hollick
Murphy Student Svc | 00-06186.00 | 202090604 |  | 0983-003 | Site Lighting | Building Permit | 2020-05-29 | 2020-08-03 | 1 | OD | Hollick, Parmelee
Nesbitt Academic Ctr | 00-06186.00 | 202090608 |  | 0983-013 | Site Lighting | Building Permit | 2020-05-29 | 2020-08-03 | 1 | OD | Hollick, Parmelee
Science | 00-06186.00 | 202090606 |  | 0983-004 | Site Lighting | Building Permit | 2020-05-29 | 2020-08-03 | 1 | OD | Hollick, Parmelee
Student Commons | 00-07104.00 |  |  | 0983-002 | Grease Interceptor Install | Rejected |  | 2020-02-25 | 1 | OD | Andy Ritter
Student Commons | 00-07104.00 |  |  | 0983-002 | Grease Interceptor Install | Rejected |  | 2020-06-08 | 1 | OD
Student Commons | 00-07104.00 | 202000668 |  | 0983-002 | Grease Interceptor Install | C of O |  | 2020-08-07 | 2 | OD | Andy Ritter
Water Tower | 00-06186.00 | 202090605 |  | 0983-029 | Site Lighting | Building Permit | 2020-05-29 | 2020-08-03 | 1 | OD | Hollick, Parmelee
WORTHINGTON-SCRANTON CAMPUS 0982-000
Engineering Bldg | 00-06614.00 | 202000217 |  | 0982-086 | Renovations to Grainger Bldg - Addition | Building Permit | 2020-02-12 | 2020-03-11 | 2 | OD
Engineering Bldg | 00-06614.00 | 202000218 |  | 0982-086 | Reno to Grainger Bldg - Partial Occupancy | Building Permit | 2020-02-12 | 2020-03-11 | 2 | OD
Engineering Bldg | 00-06614.00 | 202000743 |  | 0982-086 | Reno to Grainger Bldg - Revisions | Building Permit |  | 2020-08-13 | 2 | OD | Hollick
Multipurpose Bldg | 00-07211.00 | 202090589 |  | 0982-003 | Roof Replacement | Building Permit | 2020-06-01 | 2020-07-16 | 1 | OD | Hollick
Multipurpose Bldg | 00-07211.00 | 202000974 | 540463 | 0982-003 | Roof Fall Protection | Building Permit |  | 2020-10-08 | 2 | OD | Hollick
Study/Learning Ctr | 00-06915.00 | 202000406 |  | 0982-004 | SLC Conference Room Reno | Building Permit |  | 2020-06-05 | 2 | OD
YORK CAMPUS 0964-000
Pullo Arts Ctr | 00-07334.00 | 202000525 |  | 0964-007 | Police Services Reno | Building Permit |  | 2020-07-10 | 2 | OD
Pullo Arts Ctr | 00-07334.00 | 202000782 |  | 0964-007 | Police Services Reno - Sprinkler | Building Permit | 2020-08-01 | 2020-08-31 | 2 | OD
Pullo Arts Ctr | 00-07334.00 | 202000812 |  | 0964-007 | Police Services Reno - Fire Alarm | Building Permit | 2020-08-01 | 2020-09-04 | 2 | OD