## University Park
UNIVERSITY PARK CAMPUS 2022
BUILDING NAME | PSU Proj.# | Permit # | L&I File# | Bldg.# | Description | Status | Date Sent to L&I | Date Returned | Level of Permit | Design Services / Outside Designer
101 North Atherton Bldg | 00-08709.00 | 202200519 | 545808 | 0068-000 | Building Upgrades | Building Permit | 2022-05-19 | 2022-06-30 | 2 | DS | Derek Leonard | Bucha, McCoy, Pete
Academic Projects | 00-08360.00 | 202200139 | 545066 | 0407-000 | Lab 004C Reno - ARCH | Building Permit | 2022-02-01 | 2022-02-17 | 2 | OD | Brian Hayes
Academic Projects | 00-08360.00 | 202200138 | 545117 | 0407-000 | Lab 004C Reno - MEP | Building Permit | 2022-02-01 | 2022-02-17 | 2 | OD | Brian Hayes
Ag Arena | N/A |  |  | 0130-000 | Wireless Telecom Upgrades (AT&T) | REJECTED | 2022-08-01 | 2022-09-08 | 2 | OD | Mercandetti, Wright
Ag Science and Industry | 00-08816.00 | 202290522 | 546232 | 0116-000 | Lab 227 Muffle Furnace Install | Building Permit | 2022-07-18 | 2022-08-17 | 1 | OD | Morgan VanOuse
Ag Science and Industry | 00-08816.00 | 202290518 | 546231 | 0116-000 | Lab 441 Muffle Furnace Install | Building Permit | 2022-07-18 | 2022-08-17 | 1 | OD | Morgan VanOuse
Ag Science and Industry | 00-08795.00 | 202201198 | 547298 | 0116-000 | Elevator Replacement | Building Permit | 2022-11-16 | 2022-12-21 | 2 | DS | Ron Perttu | Dan Aumiller
Ag Science and Industry | 00-08961.00 | 202201215 | 547337 | 0116-000 | Elec System Renewal | Building Permit | 2022-11-18 | 2023-01-09 | 2 | OD | Jeff Spackman
Airport Hangar III | 00-08195.00 | 202200178 | 545102 | 0963-019 | COE Wind Tunnel - Fire Alarm | Building Permit | 2022-02-10 | 2022-03-02 | 2 | OD | Brian Hayes
Animal Diagnostics Lab | 00-08113.00 | 202200136 | 545073 | 0169-002 | Lab 8, 10 & 11 Reno - Partial Occupancy | Building Permit | 2022-02-01 | 2022-03-02 | 2 | DS | Morgan VanOuse | Forrest Rishel
Animal Diagnostics Lab | 00-08113.00 | 202200184 | 545119 | 0169-002 | Lab 8, 10 & 11 Reno - Plan Revision Sink Install | Building Permit | 2022-02-11 | 2022-03-02 | 2 | DS | Morgan VanOuse | Forrest Rishel
Animal Diagnostics Lab | 00-08450.00 | 202200316 | 545413 | 0169-002 | Histology Lab Rm 9 Upgrades (drawings only) | Building Permit | 2022-03-25 | 2022-04-25 | 2 | OD | Morgan VanOuse
ARL 3011 Research Dr | 00-08222.00 | 202200626 | 545764 | 0996-050 | Project Ferrari | Building Permit | 2022-05-22 | 2022-07-26 | 2 | OD | Matt Leah |  | Jim Young
ARL 3011 Research Dr | 00-08222.00 | 202201108 | 547237 | 0996-050 | Project Ferrari - Fire Alarm | Building Permit |  | 2022-12-02 | 2 | OD | Matt Leah
ARL 3011 Research Dr | 00-08222.00 | 202201110 | 547077 | 0996-050 | Project Ferrari - Sprinkler | Building Permit |  | 2022-12-27 | 2 | OD | Matt Leah
Beaver Stadium | 00-04533.00 | 202200222 | 545093 | 0812-000 | Suites Cooler Addition | Building Permit | 2022-02-08 | 2022-03-17 | 2 | OD | Terry Hansel |  | Ben B
Beaver Stadium | 00-04533.00 | 202200161 | 545069 | 0812-000 | Gate C Plaza Expansion | Building Permit | 2022-02-08 | 2022-03-02 | 2 | OD | Terry Hansel
Beaver Stadium | 00-04533.00 | 202200201 | 545068 | 0812-000 | Concession Stand 10 & 21 Fryers | Building Permit | 2022-02-08 | 2022-03-08 | 2 | OD | Terry Hansel |  | Steve Merrick
Beaver Stadium | 00-04533.00 |  |  | 0812-000 | South Upper Concourse | Building Permit |  | 2022-05-26 | 2 | OD | Dave Peck
Beef/Sheep Admin & Barns | 00-08829.00 | 202201138 | 547259 | 0165-004 | Electrical System Renewal | Building Permit | 2022-11-09 | 2022-12-05 | 2 | DS | Jeff Spackman | Brian B., Bob Z.
Biglar Hall | 00-06750.00 | 202200625 | 545984 | 0249-000 | Building Reno - Sprinkler (drawings only) | Building Permit |  | 2022-08-22 | 2 | OD | Rich O'Donald
Biglar Hall | 00-06750.00 | 202200991 | 546726 | 0249-000 | Building Reno Ph 2B - Plan Revision | Building Permit |  | 2022-10-26 | 2 | OD | Rich O'Donald
Biglar Hall | 00-06750.00 | 202201015 | 546605 | 0249-000 | Building Reno Ph 2B - Fire Alarm | Building Permit |  | 2022-10-26 | 2 | OD | Rich O'Donald
Boucke | 00-08580.00 | 202201086 | 547074 | 0013-000 | Rm 328 Affirmative Ation Renovation | Building Permit | 2022-10-26 | 2022-11-28 | 2 | DS | Ron Perttu | Andy B., Pete C, Bryan O.
Bryce Jordan Center | 00-08806.00 | 202200833 | 546442 | 0045-000 | Practice Gym Storage Room | Building Permit | 2022-08-11 | 2022-09-13 | 2 | DS | Marv Bevan | Andy Bucha | Ben
Carnegie | 00-08486.00 | 202200286 | 545269 | 0704-000 | Room 121 Renovation | Building Permit | 2022-03-08 | 2022-04-21 | 2 | OD | Matt Leah
Chandlee Lab | 00-08653.00 | 202200830 | 546394 | 0408-000 | Lab 13 Cryo Cooling Mods | Building Permit | 2022-08-09 | 2022-09-08 | 2 | OD | Jason Smith |  | Jim Young
Chemical & Biomedical Engineering | 00-08306.00 | 202200225 | 545226 | 0405-002 | Lab 223 Gas Cylinder Cabinet - Sprinkler | Building Permit |  | 2022-03-22 | 2 | OD | Matt Vail
Chemical & Biomedical Engineering | 00-08306.01 | 202200363 | 545534 | 0405-002 | Lab 223 Updates | Building Permit | 2022-04-05 | 2022-05-17 | 2 | OD | Matt Vail
Chemical & Biomedical Engineering | 00-08306.00 | 202200548 | 545689 | 0405-002 | Lab 223 Updates - Fire Alarm | Building Permit |  | 2022-07-07 | 2 | OD | Matt Vail
Chemical & Biomedical Engineering | 00-08306.00 | 202101110 | 544096 | 0405-002 | Lab 223 Updates - Gas Alarm | Building Permit |  | 2022-07-21 | 2 | OD | Matt Vail
Chemical Ecology Lab | 00-08388.00 | 202201006 | 546752 | 0413-000 | Ventilation System Reno | Building Permit | 2022-09-30 | 2022-10-26 | 2 | OD | Morgan VanOuse
Chemistry | 00-08393.00 | 202200096 | 544908 | 0050-000 | Lab 515 Canopy Hood | Building Permit |  | 2022-02-08 | 2 | OD | Monica Reed |  | Ben B
Chemistry | 00-08393.00 | 202201054 | 546907 | 0050-000 | Lab 515 Canopy Hood - Elec Revision | Building Permit |  | 2022-11-14 | 2 | OD | Monica Reed |  | Ben B
Chemistry | 00-08129.00 | 202201157 | 547023 | 0965-002 | Refrigerant Management Corrective Action | Building Permit | 2022-10-24 | 2022-12-07 | 2 | DS | Tyler Payne | Ting Zhou
Coal Utilization Lab | 00-08912.00 | 202201192 | 547325 | 0022-001 | Safety Showers & Eyewashes serving Lab 101D/E & 104A/B | Building Permit | 2022-11-14 | 2022-12-21 | 2 | DS | Dwayne Rush | Adam Davis
Computer | 00-08129.00 | 202201116 | 547131 | 0009-000 | ME Rm 6 Refridgerant Mgmt | Building Permit | 2022-11-02 | 2022-12-14 | 2 | DS | Tyler Payne | Ting Zhou
Curtin Hall | 00-06750.00 | 202200996 | 546727 | 0248-000 | Ph 2B Building Reno - Plan Revision | Building Permit |  | 2022-10-26 | 2 | OD | Rich O'Donald
Curtin Hall | 00-06750.00 | 202201017 | 546606 | 0248-000 | Ph 2B Building Reno - Fire Alarm | Building Permit |  | 2022-10-26 | 2 | OD | Rich O'Donald
Curtin Hall | 00-06750.00 | 202200629 | 545983 | 0248-000 | Ph 2B Building Reno - Sprinkler (Inspector copy) | Building Permit |  | 2022-11-14 | 2 | OD | Rich O'Donald
Davey Lab | 00-06902.00 | 202200588 | 546166 | 0412-000 | Loading Dock (part of Osmond Addition) | Building Permit |  | 2022-07-14 | 2 | OD | Jeff Spackman |  | Ben B
Davey Lab | 00-08616.00 |  | 546568 | 0412-000 | Renovate R513 into Two Toilet Rooms | Rejection | 2022-09-08 | 2022-10-12 | 2 | DS | Taylor Guelich | Scot Miller
Davey Lab | 00-08616.00 | 202201087 | 546568 | 0412-000 | Renovate R513 into Two Toilet Rooms - Resubmission | Building Permit | 2022-10-24 | 2022-11-28 | 2 | DS | Taylor Guelich | Scot Miller
Deike | 00-08009.00 |  |  | 0503-000 | Building Reno | CANCELLED | 2022-06-29 |  | 2 | OD | Julie Patrick
Earth and Engineering Science | 00-08471.00 | 202200315 | 545430 | 0035-000 | Rm 401 408 Research Modifications | Building Permit | 2022-03-24 | 2022-04-27 | 2 | OD | Dwayne Rush |  | Jay Young
Earth & Engineering Science | 00-06866.00 | 202200766 | 546217 | 0035-000 | Demolition and Entrance Renovation - Sprinkler | Building Permit | 2022-07-21 | 2022-09-06 | 2 | OD | Dwayne Rush |  | Jim Young
Earth & Engineering Science | 00-08534.00 |  |  | 0035-000 | 3rd Flr Jewel Collaboration Space | Building Permit |  | 2022-10-27 | 2 | OD | Brian Hayes |  | Jim?
East Area Locker Room | 00-08896.00 | 202201225 | 547546 | 0836-000 | Laundry Room 110 Reno | Building Permit | 2022-12-05 | 2023-01-09 | 2 | OD | Marv Bevan
Eisenhower Chapel | 00-08829.00 | 202201139 | 547262 | 0006-000 | Electrical System Renewal | Building Permit | 2022-11-09 | 2022-12-05 | 2 | DS | Jeff Spackman | Brian B., Bob Z.
Eisenhower Parking Deck | 00-08277.00 | 202201214 | 547336 | 0940-000 | Elevator Construction BP 2A 00-09031.00 | Building Permit | 2022-11-21 | 2022-12-19 | 2 | DS | Ron Perttu | Dan Aumiller
Elec Eng West | 00-08198.00 | 202200333 | 545438 | 0302-000 | Campus Chilled Water Service | Building Permit | 2022-03-24 | 2022-05-05 | 2 | DS | Nate Patrick | Adam Davis | Ben B
Elec Eng West | 00-08617.00 | 202200531 | 545844 | 0302-000 | Lab 20 Modifications | Building Permit | 2022-05-31 | 2022-06-30 | 2 | OD | Julie Patrick
Elliot, James | 00-07109.00 |  |  | 0034-001 | Roof and HVAC Equipment Renewal | REJECTED |  | 2022-05-24 | 2 | OD | Christie Holloway
Elliot, James | 00-07109.00 | 202200638 | 545992 | 0034-001 | Roof and HVAC Equipment Renewal - revision | Building Permit |  | 2022-07-26 | 2 | OD | Robert Ligenfelter
Energy & Enviromental Lab | 00-08129.00 | 202201149 | 547129 | 0017-000 | Reno to Mechanical Rm 301 | Building Permit | 2022-11-02 | 2022-12-05 | 2 | DS | Tyler Payne | Ting Zhou
Eng Research and Teaching (West 2) | 00-06895.00 |  |  | 0312-000 | New Structure - Sprinkler | Pending | 2022-01-20 |  | 2 | OD | Brian Hayes
Eng Research and Teaching (West 2) | 00-06895.00 | 202200200 | 545150 | 0312-000 | New Structure - Fire Alarm | Building Permit | 2022-02-03 | 2022-03-08 | 2 | OD | Brian Hayes
Fed EX | 00-06235.00 |  |  | 0963-018 | Upgrades for Occ - Men's room 104 & new shower 104A | Rejected | 2021-12-10 | 2022-02-08 | 2 | DS | Matt Vail | Forrest, Evan C and Bob Z.
Fed EX | 00-06235.00 |  |  | 0963-018 | Upgrades for Occ - Women's room 105, kitchenette & exterior | Rejected | 2021-12-10 | 2022-02-08 | 2 | DS | Matt Vail | Forrest, Evan C and Bob Z.
Fed EX | 00-06235.00 | 202200269 | 529859 | 0963-018 | ADA Upgrades | Building Permit | 2022-02-08 | 2022-04-14 | 2 | DS | Matt Vail | Forrest, Evan C and Bob Z.
Findlay | 00-06751.00 | 202201099 | 547083 | 0277-000 | Mail Room and Loading Dock Reno | Building Permit | 2022-10-27 | 2022-11-23 | 2 | OD | Rich O'Donald
Findlay | 00-07312.00 | 202201221 | 547343 | 0277-000 | Phase 2C Building Reno | Building Permit | 2022-11-23 | 2023-01-09 | 2 | OD | Rich O'Donald
Fisher Hall | 00-06750.00 |  |  | 0260-000 | Repair Corridor Heating System | Pending | 2022-11-23 |  | 2 | OD | Rich O'Donald
Ford Bldg | 00-06769.00 | 202200113 | 544915 | 0023-000 | 2021 Elevator Upgrades | Building Permit | 2022-01-12 | 2022-02-15 | 2 | DS | Ron Perttu | Dan Aumiller
Forum Classroom Bldg | 00-08456.00 | 202200247 | 545246 | 0753-000 | Classrooms 105 & 111 Seat Replacement | Building Permit | 2022-03-02 | 2022-03-30 | 2 | DS | M. Leah Dave Barnhart | Debbie Fuller, Pete C.
Frear South | 00-06902.00 | 202200587 | 546167 | 0410-000 | Loading Dock (part of Osmond Addition) | Building Permit |  | 2022-07-14 | 2 | OD | Jeff Spackman |  | Ben B
Frear South | 00-08651.00 | 202200947 | 546567 | 0410-000 | Room 236 Reno | Building Permit | 2022-09-09 | 2022-10-12 | 2 | OD | Jason Smith |  | Ben
Garfield Water Tunnel | 00-07523.00 | 202200689 | 546218 | 0996-011 | Wave Rider | Building Permit |  | 2022-08-09 | 2 | OD | Matt Leah |  | Ben B
Garfield Water Tunnel | 00-07523.00 | 202200973 | 546565 | 0996-011 | Wave Rider - Fire Alarm | Building Permit |  | 2022-10-14 | 2 | OD | Matt Leah |  | Ben B
Grange | 00-05845.00 | 202200177 | 545092 | 0232-000 | HVAC System Reno - Fire Alarm | Building Permit |  | 2022-03-02 | 2 | OD | Ron Perttu
Grange | 00-08829.00 | 202201129 | 547251 | 0232-000 | Electrical System Renewal | Building Permit | 2022-11-09 | 2022-12-05 | 2 | DS | Jeff Spackman | Brian B., Bob Z.
Hammond | 00-08751.00 | 202200537 | 545839 | 0304-000 | Office 102O Reno | Building Permit | 2022-05-24 | 2022-06-30 | 2 | OD | Julie Patrick |  | Ben B
Hammond | 00-08751.00 | 202200728 | 546259 | 0304-000 | Office 102O Reno - door location revision (only drawings/ scan all) | Building Permit | 2022-07-19 | 2022-08-17 | 2 | OD | Julie Patrick
Hastings Hall | 00-07312.00 |  |  | 0252-000 | Phase 2C Building Reno | REJECTION | 2022-11-23 | 2023-01-09 | 2 | OD | Rich O'Donald
HUB | 00-06803.00 | 202200188 | 545131 | 0005-000 | Install FROYO Machine at SBARRO | C of O | 2022-02-10 | 1900-02-20 | 2 | DS | Matt Vail | Brian Brubaker
HUB | 00-06803.00 | 202200261 | 545317 | 0005-000 | Install FROYO Machine at SBARRO Elecrical Revision | Building Permit | 2022-03-10 | 2022-04-12 | 2 | DS | Matt Vail | Brian Brubaker
Intramural Bldg | 00-08384.00 | 202200952 | 546601 | 0804-000 | Spin Room 16 Reno | Building Permit | 2022-09-13 | 2022-10-12 | 2 | DS | Derek Leonard | Pete C., Andy B.
Jeffrey Field (soccer) | 00-08366.00 | 202200479 | 545835 | 0806-001 | Scoreboard Replacement | Building Permit |  | 2022-06-17 | SIGN | OD | Marv Bevan |  | Jay Young
Johnston Commons | 00-06750.00 |  |  | 0276-000 | Replace Domestic Hot Water Tank | Pending | 2022-11-23 |  | 2 | OD | Rich O'Donald
Lasch | 00-06882.00 | 202200226 | 545223 | 0845-000 | Building Reno and Addition - Sprinkler | Building Permit |  |  | 2 | OD | Marv Bevan
Lasch Outdoor Practice Field | 00-06878.00 | 202200703 | 546194 | 0995-108 | Renovation to Field - Revision | Building Permit |  | 2021-08-03 | 2 | OD | Marv Bevan
Lasch | 00-08754.00 | 202200785 | 546336 | 0845-000 | Reno and Addition - 1st flr locker room & 2nd flr workspace | Building Permit |  | 2022-08-25 | 2 | OD | Marv Bevan
Leonhard | 00-08755.00 | 202200888 | 546471 | 0319-000 | Room 17 Alterations | Building Permit |  | 2022-09-28 | 2 | OD | Brian Hayes |  | Ben
Machinery Storage | 00-05321.00 | 202200818 | 546388 | 0165-011 | Electrical Upgrades | C of O | 2022-09-06 | 2022-11-18 | 2 | OD | Jeff Spackman
McCoy | 00-05080.00 |  |  | 0820-000 | Bulk Chlorine Feed System | Cancelled | 2022-04-01 |  | 1 | OD | Derek Leonard
McKee Hall | 00-08481.00 | 202290111 | 545141 | 0206-000 | Slate Roof Replacement | Building Permit | 2022-02-15 | 2022-03-10 | 1 | DS | Matt Vail | Brad Halderman | Ben B.
Meats Lab | 00-082730.00 | 202200637 | 545987 | 0128-000 | Fire Alarm System Installation | Building Permit | 2022-06-17 | 2022-07-26 | 2 | DS | Jeff Spackman | Brian Brubaker | Jim Young
Millennium Science | 00-06855.00 | 202200279 | 545271 | 0038-001 | W-006 Alterations | Building Permit | 2022-03-08 | 2022-04-15 | 2 | OD | Jason Smith
Millennium Science | 00-06855.00 | 202200906 | 546523 | 0038-001 | W-006 Alterations - Partial Occupancy | C of O | 2022-08-25 | 2022-11-04 | 2 | OD | Jason Smith
Millennium Science | 00-08860.00 | 202201043 | 546730 | 0038-001 | Crystal Growth Lab N135A 2DCC Equipment | Building Permit | 2022-09-26 | 2022-11-02 | 2 | OD | Jason Smith
Mueller | 00-08597.00 | 202200021 | 544653 | 0409-000 | Rooms 514 & 606 Reno | Building Permit | 2021-12-10 | 2022-01-13 | 2 | OD | Jason Anderson
Multi-sport Indoor Track | 00-08352.00 | 202290008 | 544877 | 0846-000 | Parapet Wall and Façade Rehabilitation | C of O | 2022-02-08 | 2022-10-05 | 1 | OD | Marv Bevan
Nittany Parking Deck | 00-08299.00 | 202290117 | 545075 | 0995-060 | Roof Rehab and Fall Protection | C of O | 2022-02-01 | 2022-10-20 | 1 | DS | Kurt Coduti |  | Ben B
Old Main | 00-08235.00 | 202200291 | 545411 | 0001-000 | Room 417 Reno - Partial Occupancy | Building Permit | 2022-03-22 | 2022-04-27 | 2 | OD | Robert Ligenfelter
OPP | 00-08407.00 | 202200160 | 544997 | 0904-000 | Suite 113 Renovation | Building Permit | 2022-01-25 | 2022-03-02 | 2 | DS | Robert Ligenfelter | Deb, Jenks, Bob Z.
OPP | 00-07510.00 | 202200776 | 546254 | 0904-000 | Planning, Design & Properties relocate to room 135 | Building Permit | 2022-07-19 | 2022-08-22 | 2 | DS | Robert Ligenfelter | Deb Fuller | Jim Young
OPP | 00-08741.00 | 202200764 | 546330 | 0904-000 | Chiller Replacement | Building Permit | 2022-07-26 | 2022-08-22 | 2 | DS | Robert Ligenfelter | Helen,Pete, Brian O. | Jim Young
Osmond Lab | 00-08736.00 | 202200359 | 545471 | 0401-000 | Osmond Reno & Osmond North Early Work | Building Permit | 2022-03-24 | 2022-05-11 | 2 | OD | Jeff Spackman
Osmond Lab | 00-08509.00 | 202200435 | 545653 | 0401-000 | Lab S-13 Pit Expansion | Building Permit | 2022-04-27 | 2022-06-07 | 2 | OD | Matt Leah |  | Ben B
Osmond Lab | 00-06902.00 | 202200591 | 545778 | 0401-001 | Building Addition | CANCELLED | 2022-07-21 | 2022-12-07 | 2 | OD | Jeff Spackman |  | Ben B
Osmond Lab | 00-06902.00 | 202200589 | 546165 | 0401-000 | Building Renovation | CANCELLED | 2022-07-21 | 2022-12-07 | 2 | OD | Jeff Spackman |  | Ben B
Outreach | 00-08855.00 | 202201092 | 547076 | 0965-013 | Building Renovations | Building Permit | 2022-10-26 | 2022-11-28 | 2 | OD | Jason Smith
Packer Hall | 00-06750.00 | 202200919 | 546542 | 0247-000 | Phase 2B Reno - Sprinkler | Building Permit |  | 2022-09-28 | 2 | OD | Rich O'Donald |  | Ben
Packer Hall | 00-06750.00 | 202201018 | 546607 | 0247-000 | Phase 2B Reno - FA | Building Permit |  | 2022-12-07 | 2 | OD | Rich O'Donald
Panzar Stadium Scoreboard | 00-08508.00 | 202200265 | 545193 | 0838-000 | Scoreboard Installation | Building Permit |  | 2022-04-12 | 2 | OD | Marv Bevan
Pattee West | 00-08829.00 | 202201235 | 547558 | 0003-001 | Capital Renewal Electrical Switchgear Upgrades | Building Permit |  | 2023-01-09 | 2 | OD | Jeff Spackman
Pegula Ice Arena | 00-08627.00 | 202200616 | 545962 | 0829-000 | Gate A Video Display | Building Permit |  | 2022-07-21 | 2 | OD | Marv Bevan
Pond Lab | 00-07178.00 | 202200125 | 544944 | 0403-000 | Steam to Hot Water Conversion | Building Permit | 2022-01-18 | 2022-02-17 | 2 | DS | Derek Leonard | Helen,Pete, Adam
Reber | 00-08673.00 | 202200502 | 545750 | 0303-000 | 243 Roan Lab Reno | Building Permit |  | 2022-06-23 | 2 | OD | Julie Patrick |  | Ben
Reber | WO H593561 |  |  | 0303-000 | Equipment Electrical Upgrade | REJECTED | 2022-06-14 |  | 1 | DS | Marie Mayotte, Jason Anderson
Reber | WO H593561 | 202200863 | 546469 | 0303-000 | Rm 19 Equipment Electrical Upgrade | Building Permit | 2022-08-17 | 2022-09-22 | 2 | DS | Marie Mayotte, Jason Anderson | Pete C.
Reber | 00-08737.00 | 202200763 | 546280 | 0303-000 | Fronk Lab 221 Reno | Building Permit |  | 2022-08-22 | 2 | OD | Julie Patrick |  | Ben
Rec Hall | 00-08364.00 |  |  | 0801-000 | Wrestling Room Receptacles | Rejected | 2022-02-09 | 2022-03-02 | 1 | DS | Marv Bevan | Rupert, M. Snyder
Rec Hall | 00-08364.00 | 202200267 | 545319 | 0801-000 | Wrestling Locker Room Reno | Building Permit |  | 2022-04-12 | 2 | OD | Marv Bevan
Rec Hall | 00-07086.00 | 202200844 | 546379 | 0801-000 | ESP Detailed Design & Chilled Water Connection | Building Permit | 2022-08-09 | 2022-09-13 | 2 | OD | Tyler Payne |  | Ben
Research Unit A | 00-08663.00 | 202200412 | 545497 | 0033-000 | Renovate for the Speech & Hearing Clinic | Building Permit | 2022-04-01 | 2022-05-31 | 2 | OD | Chad Spackman
Research Unit A | 00-08663.00 | 202201194 | 547516 | 0033-000 | Speech & Hearing Clinic - Child Restroom Revision | Building Permit | 2022-10-26 | 2022-12-19 | 2 | OD | Chad Spackman
Research Unit A | 00-08663.00 | 202201106 | 547080 | 0033-000 | Renovate for the Speech & Hearing Clinic - Partial Occupancy | Building Permit | 2022-10-26 | 2022-11-28 | 2 | OD | Chad Spackman
Research Unit Modular Lab | 00-08668.00 | 202200918 | 546483 | 0033-001 | USDA Swing Space | Building Permit | 2022-08-19 | 2022-09-28 | 2 | OD | Robert Ligenfelter
Research West | 00-08380.00 | 202200210 | 545190 | 0271-000 | Room 202 Flume Reno | Building Permit |  | 2022-03-17 | 2 | OD | Matt Vail
Research West | 00-08380.00 |  | 547301 | 0271-000 | Room 202 Flume Reno - Sprinkler | Rejection |  | 2022-12-12 | 2 | OD | Matt Vail
Snyder Hall | 00-07312.00 |  |  | 0254-000 | Phase 2C Building Reno | Pending | 2022-11-23 |  | 2 | OD | Rich O'Donald
Softball Stadium (Beard Field) | 00-08365.00 | 202200478 | 545934 | 0828-000 | Scoreboard Replacement | Building Permit |  | 2022-06-14 | Sign | OD | Marv Bevan |  | Jim Young
Stone Hall | 00-07312.00 |  |  | 0253-000 | Phase 2C Building Reno | Pending | 2022-11-23 |  | 2 | OD | Rich O'Donald
Susan Welch Liberal Arts | 00-07085.00 | 202200491 | 545686 | 0703-000 | New Structure | Building Permit |  | 2022-06-17 | 2 | OD | Chad Spackman |  | Ben B
Thomas (Joab L.) | 00-07527.00 | 202201230 | 547335 | 0040-000 | Capital Systems Renewal - Elevator Construction BP 2A | Building Permit | 2022-11-21 | 2023-01-09 | 2 | DS | Ron Perttu | Dan Aumiller
Thompson Hall | 00-08707.00 | 202200390 | 545583 | 0204-000 | Fire Protection System Backflow Preventer Replacement | Building Permit | 2022-04-13 | 2022-05-26 | 2 | OD | Matt Vail |  | Ben B
University Club | 00-08758.00 | 202200721 | 546252 | 0998-010 | Demolition of Building | Building Permit | 2022-07-19 | 2022-08-11 | Demo | DS | Kurt Coduti | Jason McCoy | Jim Young
University Support Bldg 1 | 00-06806.00 | 202200832 | 546475 | 0193-002 | US and PS Dispatch & Emergency Mgmt Ctr-Partial Occup | Building Permit |  | 2022-09-15 | 2 | OD | Chad Spackman |  | Jim Young
USB II - Wireless Telecom | N/A |  |  | 0999-121 | (AT&T) New Cingular PCS | REJECTED | 2022-08-01 | 2022-09-08 | 2 | OD | Mike Mercandetti, Brittany Wright
Visitor Center | 00-08408.00 | 202200484 | 545670 | 0036-000 | Athletic Services Office Reno | Building Permit | 2022-05-11 | 2022-06-17 | 2 | OD | Jason Smith
Visitor Center | 00-08408.00 | 202201052 | 546625 | 0036-000 | Athletic Services Office Reno - Revision | Building Permit |  | 2022-11-09 | 2 | OD | Jason Smith
Westgate | 00-08838.00 | 202200821 | 546443 | 0039-000 | Lab E141 Alterations | CANCELED | 2022-08-12 | 2022-09-06 | 2 | OD | Derek Leonard
Westgate | 00-08838.00 | 202201220 | 547354 | 0039-000 | Lab E141 Alterations - Sprinkler | CANCELED |  | 2023-01-09 | 2 | OD | Derek Leonard
Westgate | 00-07434.00 | 202201126 | 546906 | 0039-000 | College of IST & SOI Reno | Building Permit | 2022-10-17 | 2022-11-30 | 2 | DS | Derek Leonard | Deb F, Jenks, Bob Z
White | 00-06619.00 | 202200151 | 545088 | 0802-000 | Gaming Room Fire Alarm & Sprinkler | Building Permit |  | 2022-02-24 | 2 | OD | Rich O'Donald, Derek Stoecklein
White | 00-05080.00 | 202200577 | 546096 | 0802-000 | Pool Chemical Storage Addition | Building Permit | 2022-04-01 | 2022-07-19 | 2 | OD | Derek Leonard
Whitmore Lab | 00-06902.00 | 202200590 | 546164 | 0406-000 | Loading Dock (part of Osmond Addition) | Building Permit |  | 2022-07-21 | 2 | OD | Jeff Spackman |  | Ben B
WPSU Radio Tower | 00-08414.00 | 202200498 | 545774 | 9999-999 | WPSU Tower Modifications | Building Permit | 2022-05-17 | 2022-06-23 | 2 | OD | Jason Smith
WWTP - TFP Aeration Tanks | 00-05991.00 | 202200035 | 544848 | 0994-021 | Demo of TFP Aeration Tanks | Building Permit | 2021-12-17 | 2022-01-20 | Demo | OD | Dave Peck
WWTP - Polymer Bldg | 00-05991.00 | 202200036 | 544850 | 0994-057 | Demo of Polymer Bldg | Building Permit | 2021-12-17 | 2022-01-20 | Demo | OD | Dave Peck
WWTP - ASP Blower Bldg | 00-05991.00 | 202200037 | 544851 | 0994-015 | Demo of Blower Bldg | Building Permit | 2021-12-17 | 2022-01-20 | Demo | OD | Dave Peck
WWTP - Activated Sludge Unit 1 | 00-05991.00 | 202200038 | 544852 | 0994-016 | Demo of Activated Sludge Unit 1 | Building Permit | 2021-12-17 | 2022-01-20 | Demo | OD | Dave Peck
WWTP - ASP Storage Shed | 00-05991.00 | 202200039 | 544853 | 0994-061 | Demo of ASP Storage Shed | Building Permit | 2021-12-17 | 2022-01-20 | Demo | OD | Dave Peck
WWTP - Chlorine Bldg | 00-05991.00 | 202200040 | 544854 | 0994-058 | Demo of Chlorine Bldg | Building Permit | 2021-12-17 | 2022-01-20 | Demo | OD | Dave Peck
WWTP - Raw Sludge Pump House | 00-05991.00 | 202200041 | 544855 | 0994-033 | Demo of Raw Sludge Pump House | Building Permit | 2021-12-17 | 2022-01-20 | Demo | OD | Dave Peck
WWTP - Anoxic Tank | 00-05991.00 | 202200042 | 544856 | 0994-046 | Demo of Anoxic Tank | Building Permit | 2021-12-17 | 2022-01-20 | Demo | OD | Dave Peck
WWTP - TFP Blower Bldg | 00-05991.00 | 202200043 | 544857 | 0994-023 | Demo of TFP Blower Bldg | Building Permit | 2021-12-17 | 2022-01-20 | Demo | OD | Dave Peck
WWTP - Activated Sludge Unit 2 | 00-05991.00 | 202200044 | 544858 | 0994-017 | Demo of Activated Sludge Unit 2 | Building Permit | 2021-12-17 | 2022-01-20 | Demo | OD | Dave Peck
WWTP - Grit Tank | 00-05991.00 | 202200148 | 545065 | 0994-019 | Demo of Grit Tank | C of C | 2022-02-03 | 2022-06-10 | Demo | OD | Dave Peck
WWTP - Grit Bldg | 00-05991.00 | 202200149 | 545064 | 0994-034 | Demo of Grit Bldg | Building Permit | 2022-02-03 | 2022-02-22 | Demo | OD | Dave Peck
WWTP - Influent Sampling Bldg | 00-05991.00 | 202200147 | 545063 | 0994-010 | Demo of Influent Sampling Bldg | C of C | 2022-02-03 | 2022-06-10 | Demo | OD | Dave Peck

## Commonwealth
CAMPUS 2022 | PSU PROJECT # | Permit # |  | BLDG. # | DESCRIPTION | STATUS | DATE SENT | DATE RETURNED | PERMIT LEVEL | DS/OD
ABINGTON CAMPUS 0979-000
Athletic Center | 00-08415.00 | 202200472 | 545685 | 0979-010 | Basement Level Reno | Building Permit | 2022-05-05 | 2022-06-14 | 2 | OD | Kyle Hollick
Athletic Center | 00-08415.00 | 202300015 | 547361 | 0979-010 | Basement Level Reno - Sprinkler | Building Permit |  | 2023-01-09 | 2 | OD | Kyle Hollick
Rydal Executive Plaza | 00-08631.00 | 202200559 | 545922 | 0998-300 | HVAC/RTU/VAV/Controls Replacement | Building Permit | 2022-06-07 | 2022-07-19 | 2 | OD | Hollick, Ritter
Woodland | 00-08710.00 |  |  | 0979-008 | Ev Charging Station | Pending | 2022-11-11 |  | 2 | OD | Ritter
ALTOONA CAMPUS 0974-000
Cedar Hall | 00-08495.00 | 202290274 | 545273 | 0974-003 | Gutter and Downspout Repairs | Building Permit | 2022-03-09 | 2022-04-27 | 1 | OD | Keister, Kasper
Eiche Library | 00-07120.00 | 202290386 | 545756 | 0974-016 | Exterior Plaza Rehab | Building Permit | 2022-05-17 | 2022-06-30 | 2 | OD | William Drasher
Holtzinger | 00-08644.00 | 202200248 | 545254 | 0974-018 | Rm 108 Renovation | Building Permit | 2022-03-07 | 2022-03-30 | 2 | OD | Doug Wenger
Maple Hall | N/A | 202290384 | 545717 | 0974-008 | Rm 147 Water Heater Replacement | Building Permit | 2022-05-11 | 2022-06-30 | 2 | DS/OD | Justin Keister
Oak Hall | 00-08506.00 | 202200324 | 545427 | 0974-004 | Toilet & Bathing Facilities ADA Upgrades | Building Permit | 2022-03-23 | 2022-05-03 | 2 | OD | Justin Keister
Oak Hall | 00-08506.00 | 202200325 | 545596 | 0974-004 | New Rooftop Units 1 and 2 | Building Permit | 2022-03-23 | 2022-05-03 | 2 | OD | Justin Keister
Oak Hall | 00-08506.00 | 202200623 | 546200 | 0974-004 | Toilet & Bathing ADA Upgrades - Fire Alarm | Building Permit | 2022-07-08 | 2022-07-26 | 2 | OD | Justin Keister
Oak Hall | 00-08506.00 | 202200599 | 545960 | 0974-004 | Toilet & Bathing ADA Upgrades - Sprinkler | Building Permit |  | 2022-07-28 | 2 | OD | Justin Keister
Port Sky Café | 00-07255.00 | 202290281 | 545407 | 0974-007 | Domestic Boiler Replacement | Building Permit | 2022-03-22 | 2022-05-03 | 1 | DS/OD | Justin Keister | Mike Rupert
Port Sky Café | 00-08619.00 | 202290382 | 545662 | 0974-007 | Drain and Drain Piping Mods | Building Permit | 2022-04-27 | 2022-07-05 | 1 | DS/OD | Keister, Kasper
BEAVER CAMPUS 0986-000
Classroom Building | 00-06839.00 | 202200164 | 545005 | 0986-006 | Building Renovation | Building Permit | 1930-01-28 | 2022-03-02 | 2 | OD | Marcus Marasco
BEHREND CAMPUS 0972-000
Erie Hall (Replacement building) | 00-06840.00 | 202201221 | 547343 | 0972-015 | Partial Occupancy | Building Permit |  | 2023-01-09 | 2 | OD | Marcus Marasco
Hammermill/Zurn | 00-08492.00 |  |  | 0972-022 | Roof Top Unit Replacement | Pending | 2022-11-04 |  | 2 | OD | Marcus Marasco
Knowledge Park Bldg# 4 | N/A | 202200032 | 544836 | 0972-000 | VertMarkets - Restroom Install | Building Permit |  | 2022-01-28 | 2 | OD | Christi VanDyke, Chuck Peters
Multi-tenant Bldg# 4 @ Knowledge Park | 00-08451.00 | 202200447 | 545661 | 0972-156 | Trucklite - Sprinkler | Building Permit |  | 2022-06-14 | 2 | OD | Dennis Wilkins, chuck peters
Nick Building | 00-08492.00 |  |  | 0972-020 | Roof Top Unit Replacement | Pending | 2022-11-04 |  | 2 | OD | Marcus Marasco
Advanced Manufacturing & Innovation Ctr Bldg# 7 | 00-08419.00 | 202200199 | 545091 | 0972-181 | Trucklite Fit-out - Lab Space Corridor Fitout | Building Permit |  | 2022-03-08 | 2 | OD | Dennis Wilkins WMF
Advanced Manufacturing & Innovation Ctr Bldg# 7 | 00-08419.00 | 202200448 | 545882 | 0972-181 | Trucklite Fit-out - Sprinkler | Building Permit |  | 2022-06-14 | 2 | OD | Dennis Wilkins, chuck peters
Parking Deck (Red C) | 00-08398.00 | 202201145 | 547236 | 0972-161 | Fall Protection | Building Permit |  | 2022-12-05 | 2 | OD | James Hoover
Senat Hall | 00-06817.00 | 202200621 | 545952 | 0972-026 | Building Reno due to Moisture | Building Permit | 2022-06-16 | 2022-07-21 | 2 | OD | Keister
Witkowski, Fasenmyer, Prischak, Benson, Roche Hall (Erie Science Complex) | 00-08492.00 | 202201196 | 547313 | 0972-080 thru 0972-083, 0972-182 | Roof Top Unit Replacement | Building Permit | 2022-11-04 | 2022-12-21 | 2 | OD | Marcus Marasco
BERKS CAMPUS 0980-000
Beaver Athletics & Wellness Ctr | 00-06497.00 | 202290970 | 547086 | 0980-002 | Roof Replacement | Building Permit | 2022-10-25 | 2022-12-03 | 2 | OD | Hollick, Ritter
Sage Hall | 00-08531.00 | 202200304 | 545396 | 0980-064 | HVAC System Upgrade | Building Permit | 2022-03-17 | 2022-04-27 | 2 | OD | Justin Keister
BRANDYWINE CAMPUS 0989-000
Main Bldg | 00-05952.00 |  |  | 0989-001 | Site Lighting Upgrades | Pending | 2022-05-09 |  | 1 | DS | Andy Ritter
Vairo Library | 00-08545.00 | 202200714 | 546273 | 0989-004 | Chiller Replacement | Building Permit |  | 2022-08-09 | 2 | OD | Kyle, Hollick
Vairo Library | 00-08546.00 | 202200993 | 546272 | 0989-004 | Fire Alarm System Replacement | Building Permit | 2022-08-11 | 2022-10-26 | 2 | OD
Vairo Library | 00-08695.00 | 202201175 | 547280 | 0989-004 | EV Charging Station | Building Permit | 2022-11-16 | 2022-12-14 | 2 | OD | Andy Ritter
CAPITAL(Harrisburg) CAMPUS 0985-000
Conestoga House | 00-08528.00 |  |  | 0985-037 | Bathroom Reno | Rejected | 2022-03-11 | 2022-04-20 | 1 | OD | Justin Keister
Conestoga House | 00-08528.00 | 202290288 | 545336 | 0985-037 | Bathroom Reno | Building Permit |  | 2022-05-05 | 1 | OD | Justin Keister
Muncy House | 00-08528.00 |  |  | 0985-036 | Bathroom Reno | Rejected | 2022-03-11 | 2022-04-20 | 1 | OD | Justin Keister
Muncy House | 00-08528.00 | 202290289 | 545337 | 0985-036 | Bathroom Reno | Building Permit |  | 2022-05-05 | 1 | OD | Justin Keister
Nittany Village Residence C | 00-06741.00 | 202200393 | 545592 | 0985-112 | Laundry Room Reno - Revision | C of O | 2022-05-26 | 2022-10-17 | 2 | OD | Justin Keister
Library & Classroom Bldg | 00-08550.00 |  |  | 0985-026 | Roof Replacement | Pending | 2022-10-14 |  | 1 | OD | Wenger, Krause
Olmsted | 00-08303.00 |  |  | 0985-001 | W210/210A Electrical Circuit | Rejected | 2022-01-28 | 2022-02-17 | 2 | OD | Wenger, Krause
Olmsted | 00-08303.00 | 202200272 | 545056 | 0985-001 | W210/210A Electrical Circuit - Resubmission | Building Permit | 2022-03-04 | 2022-04-21 | 2 | OD | Wenger, Krause
Olmsted | 00-08723.00 | 202290277 | 545354 | 0985-001 | Roof Replacement | Building Permit | 2022-03-17 | 2022-05-03 | 1 | OD | John Krause
Olmsted | 00-08515.00 | 202200471 | 545682 | 0985-001 | Electric Lines Medium Voltage Gear Replacement (DO) | Building Permit | 2022-05-09 | 2022-06-10 | 2 | OD | John Krause
Olmsted | 00-08734.00 | 202200477 | 545706 | 0985-001 | W117 Reno | Building Permit | 2022-05-09 | 2022-06-17 | 2 | OD | John Krause, Doug Wenger
Olmsted | 00-08748.00 | 202200622 | 546163 | 0985-001 | W225 Office Suite | Building Permit |  | 2022-07-26 | 2 | OD | Wenger, Krause
Pine House | 00-08528.00 |  |  | 0985-038 | Bathroom Reno | Rejected | 2022-03-11 | 1902-08-28 | 1 | OD | Justin Keister
DICKINSON SCHOOL OF LAW-CARLISLE 0991-000
DUBOIS CAMPUS 0976-000
Multipurpose Bldg | 00-06709.00 | 202200048 | 544646 | 0976-007 | PAW Center Addition & Reno - Fire Alarm | Building Permit |  | 2022-01-25 | 2 | OD | Doug Wenger
Multipurpose Bldg | 00-06709.00 | 202200094 | 544931 | 0976-007 | PAW Center Addition & Reno - Sprinkler | Building Permit |  | 2022-02-08 | 2 | OD | Doug Wenger
FAYETTE CAMPUS 0984-000
FRUIT RESEARCH CENTER 0968-000
Headhouse | 00-08538.00 | 202200191 | 545138 | 0968-011 | Door Replacement | C of O | 2022-03-08 | 2023-02-01 | 2 | OD | John Krause
Musselman | 00-08538.00 | 202200190 | 545137 | 0968-020 | Door Replacement | Building Permit |  | 2022-03-08 | 2 | OD | John Krause
Musselman | 00-08818.00 | 202200913 | 546530 | 0968-020 | 1st Flr Abatement & New Ceiling | Building Permit | 2022-08-30 | 2022-09-28 | 2 | OD | John Krause
Musselman | 00-08818.00 | 202200915 | 546531 | 0968-020 | 2nd Flr Abatement & New Ceiling | Building Permit | 2022-08-30 | 2022-09-23 | 2 | OD | John Krause
Rouzer House | 00-08794.00 | 202200861 | 546349 | 0968-000 | Demo of Structure | C of C | 2022-07-29 | 2023-02-01 | Demo | OD | Wenger, Krause
GRAPE RESEARCH 0967-000
GREAT VALLEY 0993-000
Graduate Center | 00-07468.00 |  |  | 0993-001 | Elevator Equipment Upgrades | REJECTED | 2022-05-19 |  | 1 | DS | Andy Ritter | Dan Aumiller
Graduate Center | 00-07468.00 | 202200744 | 546258 | 0993-001 | Elevator 1 and 2 Upgrades | Building Permit | 2022-07-19 | 2022-08-11 | 2 | DS | Andy Ritter | Dan Aumiller
Graduate Center | 00-08696.00 |  |  | 0993-001 | EV Charging Stations | Pending | 2022-11-11 |  | 2 | OD | Andy Ritter
GREATER ALLEGHENY CAMPUS 0978-000
Frable | 00-06872.00 | 202290125 | 545221 | 0978-004 | Roof and Canopy EPDM Replacement | Building Permit |  | 2022-03-22 | 1 | OD | Ron Kobelenske
Student Community Ctr | 00-07232.00 | 202200552 | 545822 | 0978-006 | Lounge/Lower Level Reno | Building Permit |  | 2022-07-07 | 2 | OD | Marcus Marasco
Ostermayer Lab | 00-06375.00 | 202200182 | 545071 | 0978-012 | RTU Access Platform | Building Permit |  | 2022-03-08 | 2 | OD | Marcus Marasco
HAZLETON CAMPUS 0973-000
Charles T Butler Teaching Facility | 00-08210.00 | 202200330 | 545420 | 0973-015 | Ground Floor Reno | Building Permit |  | 2022-05-05 | 2 | OD | Kyle Hollick
Water Tower | 00-06827.00 | 202200111 | 544924 | 0973-044 | Reburbishment | Building Permit | 2022-01-13 | 2022-02-15 | 2 | DS | Kyle Hollick | McCoy, Manning, Brubaker
HERSHEY 0990-000
LEHIGH VALLEY 0977-000
Lehigh Valley Bldg | 00-08265.00 | 202200214 | 545191 | 0977-100 | IT Office Reno | Building Permit |  | 2022-03-17 | 2 | OD | Andy Ritter
Lehigh Valley Bldg | 00-05383.00 | 202200604 | 545953 | 0977-100 | Emergency Lighting Upgrades | Building Permit | 2022-06-13 | 2022-07-21 | 2 | OD | Andy Ritter
MONT ALTO CAMPUS 0971-000
Conklin Hall | 00-08568.00 | 202201196 | 547313 | 0971-002 | Elevator Upgrade | Building Permit | 2022-11-16 | 2022-12-20 | 2 | DS | Wenger, Krause | Dan Aumiller
Food Services Bldg | 00-08327.00 | 202200309 | 545421 | 0971-018 | Generator Replacement | Building Permit | 3/33/2022 | 2022-04-27 | 2 | DS | Justin Keister | Pete C.
Multipurpose Activities Center (MAC) | 00-08569.00 | 202200192 | 545139 | 0971-021 | Door Replacement | Building Permit |  | 2021-03-08 | 2 | OD | Doug Wenger
Residence B | 00-08551.00 | 202200465 | 545678 | 0971-007 | Knob and Tube Replacement | Building Permit | 2022-05-09 | 2022-06-17 | 2 | OD | John Krause
NAVY YARD
NEW KENSINGTON 0981-000
Administration Bldg | 00.08106.00 | 202200012 | 544641 | 0981-005 | Abatement | Building Permit | 2021-12-06 | 2022-01-13 | 2 | OD | Marcus Marasco
Engineering Bldg | 00-08729.00 | 202200597 | 545954 | 0981-002 | Classroom 133 Abatement Restoration | Building Permit | 2022-06-10 | 2022-07-28 | 2 | OD | Marcus Marasco, Ron Kobelenske
Science Bldg | 00-06164.00 | 202200600 | 545955 | 0981-001 | Rms 118 and 119 Abatement Restoration | Building Permit | 2022-06-10 | 2022-07-28 | 2 | OD | Marcus Marasco, Ron Kobelenske
ROCK SPRINGS 0959-000
SCHUYLKILL CAMPUS 0975-000
Business and Academic Svcs | 00-07241.00 | 202200639 | 545988 | 0975-008 | Exterior Stair Replacement | Building Permit | 2022-06-16 | 2022-07-26 | 2 | DS | Hollick, Ritter | McCoy
Classroom Bldg | 00-07366.00 | 202290971 | 547084 | 0975-005 | Roof Replacement | Building Permit | 2022-10-26 | 2022-12-05 | 1 | OD | Hollick, Ritter
Classroom Bldg | 00-07366.00 | 202201143 | 547235 | 0975-005 | Rooftop Fall Protection | Building Permit |  | 2022-12-05 | 1 | OD | Andy Ritter
SHAVERS CREEK 0960-000
Stone Valley Forest Camp Parking Areas | 00-08461.00 |  |  |  | Parking Lot Improvements(EV Charger & Blue Lt phone) | Rejection |  | 2022-10-12 | 2 | OD | Doug Wenger
Stone Valley Forest Camp Parking Areas | 00-08461.00 | 202201053 | 546947 | 0960-000 | Parking Lot Improvements(EV Charger & Blue Lt phone) | Building Permit |  | 2022-11-14 | 2 | OD | Bill Drasher
SHENANGO CAMPUS 0987-000
Forker Lab | 00-06910.00 | 202290545 | 546341 | 0987-001 | Roof Replacement | Building Permit | 2022-07-29 | 2022-09-06 | 1 | OD | Marasco, Kobelenske
WARMINSTER 0998-000
WILKES-BARRE CAMPUS 0983-000
Athletic & Rec Building | 00-08309.00 | 202290280 | 545399 | 0983-011 | Site lighting | Building Permit | 2022-03-15 | 2022-05-03 | 1 | OD | William Drasher
Commons Bldg | 00-08930.00 | 202290660 | 546638 | 0983-002 | Roof top Unit Replacement | Building Permit | 2022-09-20 | 2022-11-07 | 1 | DS | Bill Drasher
Hayfield House | 00-08309.00 | 202290279 | 545398 | 0983-001 | Site lighting | Building Permit | 2022-03-15 | 2022-05-03 | 1 | OD | William Drasher
Science Bldg | 00-08309.00 | 202290278 | 545397 | 0983-004 | Site lighting | Building Permit | 2022-03-15 | 2022-05-03 | 1 | OD | William Drasher
Science Bldg | N/A | 202290304 | 545563 | 0983-004 | Electrical Circuit in Rm 112 | Building Permit | 2022-04-12 | 2022-05-26 | 1 | DS | Kyle Hollick
Treatment Plant | 00-06832.00 | 202200432 | 545636 | 0983-028 | Electrical Upgrades | Building Permit | 2022-04-25 | 2022-06-07 | 2 | OD | Andy Ritter
Treatment Plant | 00-06832.00 |  |  | 0983-028 | Heating Upgrades | Pending | 2022-12-08 |  | 2 | OD | Ritter, Hollick
Veterans Memorial Plaza | 00-07361.00 | 202200262 | 545318 | 0983-078 | New Structure | Building Permit | 2022-03-08 | 2022-04-07 | 2 | DS | Kyle Hollick | Jason McCoy
SCRANTON CAMPUS 0982-000
Engineering Bldg | 00-06614.00 | 202200732 | 546278 | 0982-006 | Electrical Upgrades | Building Permit |  | 2022-08-11 | 2 | OD | Hollick, Ritter
Athletics Field - soccer | 00-08867.00 |  |  | 0982-053 | Data and Power Upgrades | REJECTED | 2022-07-08 | 2022-07-28 | 1 | OD | Drasher, Hollick, Ritter
Athletics Field - soccer | 00-08867.00 | 202200795 | 546458 | 0982-053 | Data and Power Upgrades | Building Permit | 2022-08-22 | 2022-08-31 | 1 | OD | Drasher, Hollick, Ritter
Sign Permit - by Engineering Bldg | 00-07488.00 | 202200089 | 544914 | 0982-055 | Landmark Sign (near Engineering Bldg) | Sign Permit | 2022-01-12 | 2022-02-01 | 2 | DS | Kyle Hollick | Jason McCoy
Library Classroom | 00-06825.00 | 202201224 | 547319 | 0982-002 | Library Classroom Bldg Reno | Building Permit | 2022-11-15 | 2023-01-09 | 2 | OD | Kyle Hollick
Multipurpose Bldg | 00-08572.00 |  |  | 0982-003 | Gym Floor Replacement and Batting Cage Install | Rejection | 2022-05-06 | 2022-06-23 | 1 | DS | Hollick, Drasher
Multipurpose Bldg | 00-08572.00 | 202290509 | 545701 | 0982-003 | Power Vent Airflow blowers installed in gym floor | C of C | 2022-06-30 | 2023-01-20 | 1 | DS | Hollick, Drasher
Tennis Courts | 00-08211.00 | 202200260 | 545320 | 0982-052 | Lighting Improvements | Building Permit |  | 2022-04-05 | 2 | OD | Kyle Hollick
YORK CAMPUS 0964-000
Pullo | 00-08578.00 | 202290273 | 545272 | 0964-007 | Install Skylights | Building Permit | 2022-03-10 | 2022-04-27 | 1 | OD | John Krause