## University Park
UNIVERSITY PARK CAMPUS 2023
BUILDING NAME | PSU Proj.# | Permit # | L&I File# | Bldg.# | Description | Status | Date Sent to L&I | Date Returned | Level of Permit | Design Services / Outside Designer
101 North Atherton Bldg | 00-08709.00 | 202300157 | 547844 | 0068-000 | Building Upgrades - Scope of Work Reduction | Building Permit | 2023-01-18 | 2023-02-15 | 2 | DS | Derek Leonard | Pete Caporuscio
Ag Science | 8795 & 6768 | 202300172 | 547869 | 0116-000 | 2021 Elevator Upgrades - sprinkler revision | Building Permit | 2023-01-23 | 2023-02-20 | 2 | DS | Ron Perttu | Dan Aumiller
Applied Research Lab | 911300 | 202300660 | 549227 | 0996-010 | Project Achilles "one-stop-stop" | Building Permit |  | 2023-06-26 | 2 | OD | Matt Leah
ARL 3011 Research Dr | 00-08222.00 | 202300249 | 548006 | 0996-050 | Project Ferrari - Partial Occupancy | Building Permit |  | 2023-03-08 | 2 | OD | Matt Leah
ARL West I (3075 Research Dr) | 851400 | 202300473 | 547908 | 0996-019 | Project United | Building Permit | 2023-01-30 | 2023-05-10 | 2 | OD | Matt Leah
Atherton Hall | 886900 | 202300312 | 548113 | 0233-000 | Schreyer Honoro College - Refresh Common Areas | Building Permit | 2023-03-03 | 2023-03-27 | 2 | OD | Matt Vail
Atherton Hall | 905700 | 202300566 | 549067 | 0233-000 | Schreyer Honoro College - Renovate Rooms C007 & C008 | Building Permit | 2023-05-17 |  | 2 | DS | Matt Vail | Forrest Rishel
Athletic Admin | 840800 | 202300382 | 548199 | 0036-000 | Athletic Services Office Reno | Building Permit | 2023-04-14 |  | 2 | OD | Jason Smith
Bank of America Bldg (Career Services) | 887400 | 202300412 | 548382 | 0042-000 | Rm 237 Gender Neutral Restroom | Building Permit | 2023-04-04 | 2023-04-24 | 2 | OD | Derek Leonard | Lara Glembock
Beaver Stadium | 453300 | 202300475 | 548386 | 0812-000 | VIP Suites and Club Level Bars | Building Permit | 2023-04-06 | 2023-05-10 | 2 | OD | David Peck | John Volence Pete Brumburgh |  | Steve Merrick
Beaver Stadium | 899800 | 202300463 | 548593 | 0812-000 | Letterman's Legacy Plaza Lighting | Building Permit | 2023-04-17 | 2023-06-28 | 2 | OD | Marv Bevan
Beaver Stadium | 924900 |  |  | 0812-000 | Club level Family Restroom & Wellness Room | Pending | 2023-06-14 |  | 2 | OD | David Peck
Bennet Family Child Care | 883100 |  |  | 0041-000 | Playground Shade Structure | Pending | 2023-07-17 |  | 2 | DS | Alan Zimmerman | Musser, Dinger
Biglar Hall | 675000 | 202300606 | 549133 | 0249-000 | Temporary Electrical Bulletin 7 Plan Rev | Building Permit | 2023-05-25 | 2023-06-16 | 2 | OD | Rich O'Donald
BJC | 914100 | 202300392 | 548347 | 0045-000 | East Switchgear Power Distribution Upgrades | Building Permit | 2023-03-21 | 2023-04-17 | 2 | OD | Tyler Payne
Business Bldg | 830000 | 202300314 | 547964 | 0023-001 | MBA Classroom Renovation | Building Permit |  | 2023-03-27 | 2 | OD | Robert Ligenfelter
Chandlee Lab | 00-08653.00 | 202300443 | 548443 | 0408-000 | Lab 13 Cryo Cooling Mods - Revision | C of O | 2023-05-01 | 2023-07-18 | 2 | OD | Jason Smith
Chemical & Biomedical Engineering | 00-08306.00 | 202300250 | 547905 | 0405-002 | Lab 223 Updates - Plan Revision | C of O | 2023-03-08 | 2023-03-20 | 2 | OD | Matt Vail | Richard Koval
Computer Bldg | H773264 | 202390556 | 548449 | 0009-000 | Fire Alarm Replacement | Building Permit | 2023-03-20 | 2023-05-08 | 2 | DS | Scott Webster | Mike Rupert
Curtin Hall | 675000 | 202300605 | 549132 | 0249-000 | Temporary Electrical Bulletin 7 Plan Rev | Building Permit | 2023-05-25 | 2023-06-22 | 2 | OD | Rich O'Donald
Dairy Barn D | 00-05321.00 | 202300066 | 547600 | 0168-004 | Grinder Booth Install | Building Permit | 2022-12-14 | 2023-01-23 | 2 | OD | Jeff Spackman
Dairy Barn F/E | 826900 | 202300575 | 548853 | 0168-006 | Plumbing Alterations | Building Permit |  | 2023-06-01 | 2 | OD | Jason Smith
Daybridge | H773257 | 202390334 | 548303 | 0965-004 | Fire Alarm Replacement | Building Permit | 2023-03-27 | 2023-04-17 | 2 | DS | Scott Webster | Mike Rupert
Deike | 00-08009.00 | 202300065 | 547284 | 0503-000 | Building Reno - Resubmission | Building Permit | 2022-11-14 | 2023-01-23 | 2 | OD | Julie Patrick
Deike | 900500 |  |  | 0503-000 | Renovate Rooms 101, 102 &105 | Pending | 2023-07-11 |  | 2 | OD | Ron Perttu | Scot Miller, Caparusio
Earth & Engineering Science | 00-08471.00 | 202300055 | 547334 | 0035-000 | Labs 204, 306, 401 & 402 Renovations | Building Permit | 2022-11-21 | 2023-01-23 | 2 | OD | Dwayne Rush
Earth & Engineering Science | 895700 | 202300389 | 548213 | 0035-000 | Rm 215 Kitchen Reno | Building Permit | 2023-03-15 | 2023-04-17 | 2 | OD | Julie Patrick
East Area Locker Room | 866500 | 202300653 | 549276 | 0836-000 | Roof Replacement Sections 1-4 & 8 | Building Permit | 2023-05-25 | 2023-06-28 | 2 | DS | Marv Bevan | Brad Holderman
East Parking Deck | 833100 | 202300360 | 548341 | 0995-087 | Parking Garage Upgrades | Building Permit | 2023-03-14 |  | 2 | OD | Kurt Coduti
Eisenhower Chapel | 887500 |  |  | 0006-000 | Gender Neutral Restrooms | Pending | 2023-04-10 |  | 2 | OD | Derek Leonard | Lara Glembock
Eisenhower Parking Deck | 868200 | 202390559 | 548447 | 0940-000 | Parking Deck Rehabilitation | Building Permit | 2023-04-10 | 2023-05-08 | 1 | OD | Kurt Coduti | Ryan Kennedy Mary Hanes
Eng Research and Teaching (West 2) | 00-06895.00 | 202300155 | 547843 | 0312-000 | New Structure - Partial Occupancy | C of O | 2023-02-15 | 2023-03-01 | 2 | OD | Brian Hayes |  | Mike Kulbacki
Environmental Management Facility | 826900 | 202300548 | 548536 | 0994-069 | New Structure (permit Only) | Building Permit |  | 2023-05-25 | 2 | OD | Jason Smith
Findlay Hall | 863500 | 202300303 | 547992 | 0277-000 | Elevator #156 Modernization | Building Permit | 2023-02-13 | 2023-03-20 | 2 | DS | Matt Vail | Brad Holderman
Findlay Hall | 675100 | 202300355 | 548230 | 0277-000 | Mail Rm and Loading Dock - Sprinkler | Building Permit |  | 2023-04-10 | 2 | OD | Rich O'Donald
Findlay Hall | 675100 | 202300468 | 548547 | 0277-000 | Mail Rm and Loading Dock - Fire Alarm | Building Permit | 2023-04-17 | 2023-05-10 | 2 | OD | Rich O'Donald | James Kozel
Findlay Hall | 731200 | 202300449 | 548360 | 0277-000 | Mechanical Room Upgrades | Building Permit | 2023-03-30 | 2023-05-03 | 2 | OD | Rich O'Donald | Melissa Adams
Fisher Hall | 00-06750.00 | 202390004 | 547355 | 0260-000 | Repair Corridor Heating System | Building Permit | 2022-11-23 | 2023-01-18 | 1 | OD | Rich O'Donald
Ford Bldg | 00-06769.00 | 202300173 | 547870 | 0023-000 | 2021 Elevator Upgrades - sprinkler revision | Building Permit | 2023-01-23 | 2023-02-20 | 2 | DS | Ron Perttu | Dan Aumiller
Ford Bldg | 906300 | 202300331 | 548032 | 0023-000 | Roof Reconstruction | Building Permit | 2023-02-22 | 2023-03-29 | 2 | OD | Gina Rossi | Dan Aumiller
Ford Bldg | H773263 | 202390555 | 548450 | 0023-000 | Fire Alarm Replacement | Building Permit | 2023-03-20 | 2023-05-08 | 2 | DS | Scott Webster | Mike Rupert
Forest Resources Lab | 864500 | 202300524 | 548856 | 0111-000 | South Wing Renovation | Building Permit | 2023-04-27 | 2023-05-19 | 2 | OD | Kurt Coduti | Brian Schmidt
Gardner House | 08-82658.03 | 202300567 | 548975 | 0666-000 | Code Upgrades - Door Replacement Plan Revision | Building Permit | 2023-05-10 | 2023-05-31 | 2 | DS | Mike Rupert
Garfield Water Tunnel | 00-07523.00 | 202300555 | 548870 | 0996-011 | Wave Rider - Partial Occupancy 1 | Building Permit | 2023-05-01 | 2023-06-07 | 2 | OD | Matt Leah | Thorsten Sterbenz
Garfield Water Tunnel | 00-07523.00 | 202300556 | 549082 | 0996-011 | Wave Rider - Partial Occupancy 2 | Building Permit | 2023-05-01 | 2023-06-07 | 2 | OD | Matt Leah | Thorsten Sterbenz
Garfield Water Tunnel | 00-07523.00 | 202300557 | 549083 | 0996-011 | Wave Rider - Partial Occupancy 3 | Building Permit | 2023-05-01 | 2023-06-07 | 2 | OD | Matt Leah | Thorsten Sterbenz
Garfield Water Tunnel | 00-07523.00 | 202300558 | 548084 | 0996-011 | Wave Rider - Partial Occupancy 4 | Building Permit | 2023-05-01 | 2023-06-07 | 2 | OD | Matt Leah | Thorsten Sterbenz
Garfield Water Tunnel | 00-07523.00 | 202300559 | 549087 | 0996-011 | Wave Rider - Partial Occupancy 5 | Building Permit | 2023-05-01 | 2023-06-07 | 2 | OD | Matt Leah | Thorsten Sterbenz
Garfield Water Tunnel | 00-07523.00 | 202300560 | 549088 | 0996-011 | Wave Rider - Partial Occupancy 6 | Building Permit | 2023-05-01 | 2023-06-07 | 2 | OD | Matt Leah | Thorsten Sterbenz
Garfield Water Tunnel | 00-07523.00 | 202300561 | 549089 | 0996-011 | Wave Rider - Partial Occupancy 7 | Building Permit | 2023-05-01 | 2023-06-07 | 2 | OD | Matt Leah | Thorsten Sterbenz
Garfield Water Tunnel | 00-07523.00 | 202300562 | 549090 | 0996-011 | Wave Rider - Partial Occupancy 8 | Building Permit | 2023-05-01 | 2023-06-07 | 2 | OD | Matt Leah | Thorsten Sterbenz
Garfield Water Tunnel | 00-07523.00 | 202300563 | 549092 | 0996-011 | Wave Rider - Partial Occupancy 9 | Building Permit | 2023-05-01 | 2023-06-07 | 2 | OD | Matt Leah | Thorsten Sterbenz
Geary Hall | 675000 |  |  | 0246-000 | Power to Johnston Commons Dock Trash Compactor | REJECTED | 2023-01-24 | 2023-02-20 | 1 | OD | Rich O'Donald
Geary Hall | 675000 | 202300386 | 548210 | 0246-000 | Power to Johnston Commons Dock Trash Compactor | Building Permit | 2023-03-15 | 2023-04-14 | 2 | OD | Rich O'Donald
Golf Course Maintenance Facility | 877300 | 202300351 | 548017 | 0841-000 | Building Upgrade | Building Permit | 2023-02-20 | 2023-04-05 | 2 | DS | Marv Bevan | Andy Bucha
Gold Course Cold Equipment Storage | 877300 | 202300352 | 548018 | 0841-001 | Building Upgrade | Building Permit | 2023-02-20 | 2023-04-05 | 2 | DS | Marv Bevan | Andy Bucha
Golf Course Seed Storage | 877300 | 202300353 | 548019 | 0841-004 | Building Upgrade | Building Permit | 2023-02-20 | 2023-04-05 | 2 | DS | Marv Bevan | Andy Bucha
Golf Course Equipment Shed | 846500 |  |  | 0841-008 | New Structure | Pending | 2023-06-16 |  | 2 | DS | Kurt Coduti | Andy Bucha, Benson
Hamilton Hall/Waring Hall | 854700 | 202300745 | 549479 | 0205-000/0272-000 | HVAC, Parking Lot & Courtyard, & Domestic Hot Water | Building Permit |  | 2023-07-24 | 2 | OD | Rich O'Donald
Hastings Hall | 731200 | 202300440 | 547351 | 0252-000 | East Halls Ph 2C Reno | Building Permit |  | 2023-05-01 | 2 | OD | Rich O'Donald
Holuba Hall | 907900 | 202300420 | 548430 | 0833-000 | VideoBoard Installation | Building Permit |  | 2023-04-24 | 2 | OD | Marv Bevan
Hosler | 891300 | 202300233 | 547972 | 0502-000 | Emergency Shower Outside Lab 16 | Building Permit | 2023-02-08 | 2023-03-08 | 2 | DS | Dwayne Rush | Adam Davis
Housing and Food Services | 919500 |  |  | 0280-000 | Renovate Bakery Office and Storage | Pending | 2023-07-19 |  | 2 | DS | Mat Vail | D. Fuller, Pete, Bryan O
HUB | 00-08921.00 | 202300033 | 547590 | 0005-000 | Cow & Cookie Reno | CANCELLED | 2022-12-12 | 2023-01-18 | 2 | OD | Matt Vail
HUB | 00-08921.00 | 202300446 | 548377 | 0005-000 | Cow & Cookie Reno | Building Permit | 2023-04-04 | 2023-05-03 | 2 | OD | Matt Vail |  | Ben
HUB | 891700 | 202300444 | 548528 | 0005-000 | Starbucks Remodel | Building Permit | 2023-04-12 | 2023-05-01 | 2 | OD | Matt Vail | Lina Abdul-Nabi
HUB | 919200 | 202300523 | 548636 | 0005-000 | Barney's Relocation to Rm 39 | Building Permit | 2023-04-19 | 2023-06-01 | 2 | DS | Chad Spackman | Deb, Jenks, Pete | Ben
HUB | 919200 |  |  | 0005-000 | Barney's Convence Store Entry Door Upgrade | Pending | 2023-06-08 |  | 2 | DS | Chad Spackman | Deb Fuller
HUB | 912700 | 202390922 | 549222 | 0005-000 | Grand Staircase Tread Replacement | Building Permit | 2023-06-01 | 2023-06-23 | 1 | DS | Chad Spackman | Mike Rupert
HUB Parking Deck | 833100 | 202300359 | 548337 | 0995-080 | Parking Garage Upgrades | Building Permit | 2023-03-14 | 2023-04-14 | 2 | OD | Kurt Coduti
Indoor Multi-sport | 679800 | 202300306 | 548066 | 0846-000 | Netting Replacement | Building Permit | 2023-03-02 | 2023-03-20 | 2 | OD | Marv Bevan
Irvin Hall | 888700 | 202390143 | 547989 | 0203-000 | Slate Roof Replacement | Building Permit | 2023-02-13 | 2023-03-15 | 1 | DS | Matt Vail | Brad Holderman
Johnston Commons | 00-06750.00 | 202390000 | 547356 | 0276-000 | Domestic Hot Water Tank Replacment | Building Permit |  | 2023-01-18 | 1 | OD | Rich O'Donald
Johnston Commons | 675000 | 202300602 | 549138 | 0276-000 | Relocation of covered walkway roof Plan Revision | Building Permit | 2023-05-25 | 2023-06-08 | 2 | OD | Rich O'Donald
Johnston Commons | 863500 | 202300302 | 547991 | 0276-000 | Elevator #120 Modernization | Building Permit | 2023-02-13 | 2023-03-20 | 2 | DS | Matt Vail | Brad Holderman
Keller | 00-0894000 | 202300106 | 547668 | 0015-000 | Rm 104 Renovations | Building Permit |  | 2023-01-30 | 2 | OD | Taylor Guelich |  | Ben
Lasch Football Bldg | 908100 | 202300421 | 548431 | 0845-000 | Goal Post and Netting Install | Building Permit |  | 2023-04-24 | 2 | OD | Marv Bevan |  | Ben
Lasch Outdoor Pratice Field | 887200 | 202300419 | 548252 | 0995-108 | Renovations | Building Permit |  | 2023-04-24 | 2 | OD | Marv Bevan |  | Ben
Leonard Bldg | 00-0880500 | 202300093 | 547655 | 0319-000 | Room 314 Alterations | Building Permit |  | 2023-01-30 | 2 | OD | Brian Hayes |  | Ben
Medlar Field | 884700 | 202300718 | 549493 | 0827-000 | New Batter's Eye | Building Permit | 2023-06-21 | 2023-07-19 | 2 | OD | Marv Bevan
Millennium Science | 914900 | 202300693 | 549360 | 0038-001 | N-007 Laser Disconnect | Building Permit | 2023-06-14 | 2023-07-10 | 2 | OD | Jason Smith
Nittany Apt #41 | 890700 | 202390255 | 548155 | 0215-041 | Extend Circuit for Microwave | Building Permit | 2023-03-08 | 2023-03-29 | 2 | DS/OD | Matt Vail/Anna Childe
Nittany Apt #44 | 890700 | 202390253 | 548153 | 0215-044 | Extend Circuit for Microwave | Building Permit | 2023-03-08 | 2023-03-29 | 2 | DS/OD | Matt Vail/Anna Childe
Nittany Apt #45 | 890700 | 202390254 | 548154 | 0215-045 | Extend Circuit for Microwave | Building Permit | 2023-03-08 | 2023-03-29 | 2 | DS/OD | Matt Vail/Anna Childe
Nittany Parking Garage | 833100 | 202300361 | 548201 | 0995-060 | Parking Garage Upgrades | Building Permit | 2023-03-14 | 2023-04-14 | 2 | OD | Kurt Coduti
OPP Service Garage | 879200 | 202300478 | 548549 | 0904-000 | 184A Breakroom Reno | Building Permit | 2023-04-17 | 2023-05-15 | 2 | DS | Ron Perttu | Forrest, Jemks, Pete, Ryan
Osmond Lab | 00-08736.00 | 202300213 | 547865 | 0401-000 | Osmond Reno - Fire Alarm | Building Permit | 2023-01-23 | 2023-03-08 | 2 | OD | Jeff Spackman |  | Ben
Osmond Lab | 00-08736.00 | 202300120 | 547704 | 0401-000 | Osmond Reno - Scope of Work Reduction Rev | Building Permit |  | 2023-02-01 | 2 | OD | Jeff Spackman
Osmond Lab (New Physics Bldg) | 690200 |  |  | 0401-000 | Lecture Hall Reno | Pending | 2023-06-21 |  | 2 | OD | Jeff Spackman
Packer Hall | 675000 | 202300604 | 549119 | 0249-000 | Temporary Electrical Bulletin 7 Plan Rev | Building Permit | 2023-05-25 | 2023-06-16 | 2 | OD | Rich O'Donald
Palmer Museum | 00-06767.00 | 202300137 | 547726 | 0758-000 | New Structure - Fire Alarm | Building Permit |  | 2023-02-06 | 2 | OD | Monica Reed
Palmer Museum | 00-06767.00 | 202300552 | 548985 | 0758-000 | New Structure - Partial Occupancy | Building Permit | 2023-05-17 | 2023-06-07 | 2 | OD | Monica Reed
Paterno Library | 00-08797.00 | 202300438 | 548379 | 0003-003 | Entry Plaza Reconstruction | Building Permit | 2023-04-03 | 2023-05-01 | 2 | DS | Derek Leonard | Brubaker,McCoy,Dinger, Miller
Penn State Conference Ctr | 00-06071.00 | 202300086 | 547648 | 0965-001 | Walk-in Cooler Revisions | C of O | 2023-01-30 | 2023-02-10 | 2 | OD/DS | Mike Rupert
Power Plant (West Campus) | 00-06775.01 | 202300739 | 549474 | 0911-000 | Replace Condensate Tank | Building Permit | 2023-06-20 | 2023-07-19 | 2 | OD | Jeff Spackman
Rec Hall | 708600 | 202300319 | 548117 | 0801-000 | ESP and Campus Chilled Water Connection | Building Permit | 2023-03-08 | 2023-04-10 | 2 | OD | Tyler Payne
Research Unit A Modular Lab | 00-08668.00 | 202300064 | 547582 | 0033-001 | USDA Swing Space - Revision | C of O | 2023-01-23 | 2023-02-06 | 2 | OD | Robert Ligenfelter
Research Unit A | 00-09130.00 | 202390554 | 548448 | 0033-000 | Window Replacement | Building Permit | 2023-03-16 | 2023-05-08 | 1 | DS | Chad Spackman
Research West | 838000 | 202300220 | 547301 | 0271-000 | Room 202 Water Flume - Sprinkler (inspection log & drawings) | C of O |  | 2023-07-18 | 2 | OD | Matt Vail
Rotary Press Bldg (WWTP) | 8981 | 202300685 | 549299 | 0994-030 | Electrical Room HVAC | Building Permit |  | 2023-07-10 | 2 | OD | David Peck
Scheyer House | N/A | 202300130 | 547658 | 0029-000 | Elevator Installation | Building Permit |  | 2023-02-06 | Elev | OD | Mike Rupert
Shields | 906300 | 202300283 | 548010 | 0004-000 | Roof Reconstruction | Building Permit | 2023-02-20 | 2023-03-15 | 2 | DS | Gina Rossi | Dan Aumiller
Shields | 901900 | 202300476 | 548556 | 0004-000 | Suite 214 Reno | Building Permit | 2023-04-14 | 2023-05-15 | 2 | DS | Chad Spackman | Forrest, Pete C, Jenkins S.
Shields | 680200 | 202300459 | 548540 | 0004-000 | Suite 101 Kitchenette | Building Permit | 2023-04-14 | 2023-05-08 | 2 | DS | Chad Spackman
Snyder Hall | 731200 | 202300407 | 547342 | 0254-000 | East Halls Ph 2C Reno | Building Permit |  | 2023-04-24 | 2 | OD | Rich O'Donald
Sparks | 860800 |  |  | 0701-000 | R215 Mens Restroom H/C Upgrades | Pending | 2023-07-19 |  | 2 | DS | Ron Perttu | Scot Miller, Adam Davis
Stone Hall | 731200 | 202300324 | 547350 | 0253-000 | Building Reno - Ph 2C | Building Permit |  | 2023-03-29 | 2 | OD | Rich O'Donald
Technology Support Bldg | 811900 | 202300182 | 547912 | 0999-019 | Fire Pump Controller | Building Permit |  | 2023-02-22 | 2 | OD | Taylor Guelich
Wagner | 906300 | 202300307 | 548009 | 0014-000 | Roof Reconstruction | Building Permit | 2023-02-20 | 2023-03-22 | 2 | DS | Gina Rossi | Dan Aumiller
Waring Hall/Hamilton Hall | 854700 | 202300745 | 549479 | 0205-000/0272-000 | HVAC, Parking Lot & Courtyard, & Domestic Hot Water | Building Permit |  | 2023-07-24 | 2 | OD | Rich O'Donald
Wartik | 899700 | 202300305 | 548052 | 0402-000 | Rm 105, 106 & 107 GPC Upgrades | Building Permit | 2023-02-27 | 2023-03-22 | 2 | DS | Taylor Guelich | Deb Fuller
West 1 - Eng Research & Teaching | 00-06866.00 | 202300225 | 546235 | 0310-000 | New Structure - Fire Alarm | Building Permit |  | 2023-02-27 | 2 | OD | Dwayne Rush
White | 843100 | 202300671 | 549268 | 0802-000 | ESP Upgrades | Building Permit |  | 2023-06-30 | 2 | OD | Tyler Payne

## Commonwealth
CAMPUS 2023 | PSU PROJECT # | Permit # |  | BLDG. # | DESCRIPTION | STATUS | DATE SENT | DATE RETURNED | PERMIT LEVEL | DS/OD
ABINGTON CAMPUS 0979-000
Athletic Center | 00-08415.00 | 202300015 | 547361 | 0979-010 | Basement Level Reno - Sprinkler | Building Permit |  | 2023-01-09 | 2 | OD | Kyle Hollick
Athletic Center | 00-08415.00 | 202300411 | 548367 | 0979-010 | Basement Level Reno - Revised Sprinkler | Building Permit |  | 2023-04-24 | 2 | OD | Kyle Hollick
Athletic Center | 00-08055.00 | 202300223 | 547942 | 0979-010 | Rooftop Fall Protection | Building Permit |  | 2023-02-27 | 2 | OD | Andy Ritter
Lares | 878100 | 202300510 | 548306 | 0979-005 | Lubert Commons Room Renovation | Building Permit |  | 2023-05-17 | 2 | OD | Hollick, Kasper
Physical Ed Bldg | 00-08055.00 | 202390100 | 547862 | 0979-010 | Roof Repairs | Building Permit | 2023-01-23 | 2023-02-20 | 1 | OD | Andy Ritter
Rydal | 825200 | 202300445 | 548441 | 0979-003 | HVAC Upgrades | Building Permit |  | 2023-05-01 | 2 | OD | Andy Ritter | Robert Sells
Sutherland Bldg | 00-08183.00 | 202390284 | 548224 | 0979-001 | Roof Replacement | Building Permit |  | 2023-04-05 | 1 | OD | Hollick, Drasher
Sutherland Bldg | 818300 | 202300370 | 548345 | 0979-001 | Rooftop Fall Protection | Building Permit |  | 2023-04-14 | 2 | OD | Andy Ritter
Woodland Bldg | 00-08710.00 | 202300227 | 547281 | 0979-008 | Electric Vehicle Charging Station | Building Permit |  | 2023-03-08 | 2 | OD | Andy Ritter
ALTOONA CAMPUS 0974-000
Cypress Bldg | 917400 | 202300692 | 548872 | 0974-021 | ME Class Lab Renovation | Building Permit | 2023-05-03 | 2023-07-05 | 2 | OD | Doug Wenger | Aaron Jezzi
Pine Building | 892300 | 202300527 | 548596 | 0974-014 | Electrical Service Entrance Upgrade | Building Permit |  | 2023-06-28 | 2 | OD | Bill Drasher
SLEP Center | 853000 | 202300226 | 547878 | 0974-005 | ADA Chair Lift | Building Permit | 2023-02-03 | 2023-02-27 | 2 | OD | Doug Wenger
BEAVER CAMPUS 0986-000
Amphitheater | 897400 | 202300496 | 548862 | 0986-022 | Demolition of Structure | Building Permit | 2023-04-26 | 2023-05-15 | Demo | OD | Marcus Marasco | Dave Marino
Harmony Hall | 891000 | 202300179 | 547879 | 0986-007 | Bathroom Privatization (single use) | Building Permit |  | 2023-02-15 | 2 | OD | Justin Keister
Pump Station | 809200 | 202300426 | 548285 | 0986-078 | New Structure | Building Permit | 2023-03-20 | 2023-04-26 | 2 | OD | Marcus Marasco | Paul Politza
Wellness Center | 858600 | 202300448 | 548388 | 0986-009 | HVAC Upgrades | Building Permit |  | 2023-05-03 | 2 | OD | Ron Kobelenske
BEHREND CAMPUS 0972-000
Almy Hall | 871200 |  |  | 0972-077 | Emergency Generator Replacement | Pending | 2023-06-28 |  | 2 | DS | Justin Keister | Pete Caporuscio
Reed Hall | 903000 | 202390725 | 548685 | 0972-006 | Upgrade Finishes in Atrium & Event Space | Building Permit | 2023-04-19 | 2023-05-23 | 1 | OD | Marcus Marasco | Ashley Solomon
Senat Hall | 00-06817.00 | 202300209 | 547915 | 0972-026 | Building Reno - Fire Alarm | Building Permit |  | 2023-02-22 | 2 | OD | Keister
REDC Parking Deck | 901100 | 202300406 | 548356 | 0972-161 | EV Charging Stations | C of O | 2023-04-19 | 2023-07-18 | 2 | OD | James Hoover
BERKS CAMPUS 0980-000
Cedar Hall | 910700 |  |  | 0980-066 | 5-Ton Heat Pump Replacement | Pending |  | 2023-06-21 | 1 | DS | Kasper, Keister
Franco Bldg | 854300 | 202390335 | 548310 | 0980-001 | Roof Replacement | Building Permit |  | 2023-04-17 | 1 | OD | Andy Ritter
Greenbriar Hall | 910700 | 202300513 | 548414 | 0980-065 | HVAC Upgrades | Building Permit | 2023-04-11 | 2023-05-17 | 2 | OD | Keister, Kasper
BRANDYWINE CAMPUS 0989-000
Vairo Library | 697600 | 202300464 | 548433 | 0989--004 | Academic Student Success Center | Building Permit |  | 2023-05-10 | 2 | OD | Kyle, Hollick
CAPITAL(Harrisburg) CAMPUS 0985-000
Library Classroom Building | 00-08742.00 | 202300089 | 547735 | 0985-026 | Mechanical Renovations | Building Permit |  | 2023-01-30 | 2 | OD | John Krause
Hanes Library Classroom Building | 855000 | 202300598 | 549076 | 0985-026 | Fall Protection and Improvements | Building Permit |  | 2023-06-16 | 2 | OD | Wenger, Krause
Mahanoy House - Capital Village | 910800 | 202390107 | 547929 | 0985-041 | Bathroom Reno | Building Permit |  | 2023-02-22 | 1 | OD | Justin Keister
Pine House - Capital Village | 910800 | 202390106 | 547930 | 0985-038 | Bathroom Reno | Building Permit |  | 2023-02-22 | 1 | OD | Justin Keister
DICKINSON SCHOOL OF LAW-CARLISLE 0991-000
Trickett Hall | 884300 | 202300058 | 547598 | 0991-001 | Office Suite Rm 017 Conversion | Buiding Permit |  | 2023-01-23 | 2 | OD | Andy Ritter
Trickett Hall | 877900 | 202390337 | 548372 | 0991-001 | Roof Replacement | Buiding Permit | 2023-04-04 | 2023-04-26 | 1 | OD | Andy Ritter
DUBOIS CAMPUS 0976-000
FAYETTE CAMPUS 0984-000
Library | 8505 | 202300681 | 549096 | 0984-003 | MEP System Upgrade | Building Permit | 2023-05-15 | 2023-07-10 | 2 | OD | Marcus Marasco | Larry Zdinak
FRUIT RESEARCH CENTER 0968-000
GRAPE RESEARCH 0967-000
GREAT VALLEY 0993-000
Graduate Ctr | 869600 | 202300228 | 547278 | 0993-001 | Electric Vehicle Charging Station | Building Permit |  | 2023-03-08 | 2 | OD | Andy
GREATER ALLEGHENY CAMPUS 0978-000
R. Kobelenske
Frable | 859400 | 202300132 | 547721 | 0978-004 | Third Floor Corridor Reno | Building Permit | 2023-01-05 | 2023-02-06 | 2 | OD | Marcus, Kobelenske
Frable | 859400 | 202300688 | 549314 | 0978-004 | Third Floor Corridor Reno - Sprinkler | Building Permit |  | 2023-07-17 | 2 | OD | Marcus,
Student Union Bldg | 723200 | 202300150 | 547702 | 0978-006 | Lounge Renovation | Building Permit |  | 2023-02-13 | 2 | OD
HAZLETON CAMPUS 0973-000
HERSHEY 0990-000
LEHIGH VALLEY 0977-000
Lehigh Valley Bldg | 869200 | 202300128 | 547723 | 0977-100 | UPS Replacement | Building Permit |  | 2023-02-06 | 2 | OD | Andy Ritter
Lehigh Valley Bldg | 900000 | 202300300 | 548038 | 0977-100 | Biology Lab Reno | Building Permit |  | 2023-03-20 | 2 | OD | kyle hollick
MONT ALTO CAMPUS 0971-000
Residence B | 898700 | 202300397 | 548296 | 0971-007 | HVAC System Replacement | Building Permit | 2023-03-20 | 2023-04-19 | 2 | OD | Doug Wenger | Bob Sells
NAVY YARD
NEW KENSINGTON 0981-000
Arbuckle Tech | 867400 | 202390558 | 548550 | 0981-009 | Abatement | Building Permit | 2023-03-24 | 2023-05-08 | 1 | OD | Marcus Marasco
Engineering | 867400 | 202390552 | 548546 | 0981-002 | Abatement | Building Permit | 2023-03-24 | 2023-05-08 | 1 | OD | Marcus Marasco
Science Bldg | 867400 | 202390553 | 548544 | 0981-001 | Abatement | Building Permit | 2023-03-24 | 2023-05-08 | 1 | OD | Marcus Marasco
Theatre/IST | 867400 | 202390557 | 548548 | 0981-004 | Abatement | Building Permit | 2023-03-24 | 2023-05-08 | 1 | OD | Marcus Marasco
ROCK SPRINGS 0959-000
SCHUYLKILL CAMPUS 0975-000
Nittany Apartments V | 917800 | 202300733 | 549470 | 0975-035 | New Residence Life Office & Housing | Building Permit | 2023-06-16 | 2023-07-20 | 2 | OD | Justin Keister
SHAVERS CREEK 0960-000
SHENANGO CAMPUS 0987-000
Lartz Library | 858200 | 202390182 | 548059 | 0987-008 | Roof Replacement | Building Permit | 2023-03-02 | 2023-03-22 | 2 | OD | James Hoover
Lartz Library | 858200 | 202300506 | 548737 | 0987-008 | Roof Fall Protection | Building Permit | 2023-04-24 | 2023-05-17 | 2 | OD | James Hoover
Lartz Library | N/A |  |  | 0987-008 | Electrical Service Replacement | Pending | 2023-06-16 |  | 2 | DS | James Hoover | Pete Caporuscio
WARMINSTER 0998-000
WILKES-BARRE CAMPUS 0983-000
Bell Science | 705600 | 202300136 | 547741 | 0983-010 | Chiller Revision | C of O | 2023-02-06 | 2023-03-14 | 2 | OD | Bill Drasher
Bell Science | 864200 | 202300719 | 549378 | 0983-010 | Entry and Water Line Upgrades | Building Permit | 2023-06-16 | 2023-07-19 | 2 | DS | Drasher, Hollick
Treatment Plant | 00-06832.00 | 202300099 | 547580 | 0983-028 | Heating Upgrades | Building Permit | 2022-12-08 | 2023-01-30 | 2 | OD | Ritter, Hollick
Treatment Plant | 00-06832.00 | 202300571 | 548986 | 0983-028 | Heating Upgrades - Elec Revision | Building Permit |  | 2023-06-05 | 2 | OD | Ritter, Hollick
SCRANTON CAMPUS 0982-000
Library Classroom Bldg | 682500 | 202300694 | 549414 | 0982-002 | Bldg Reno - Fire Alarm | Building Permit |  | 2023-07-17 | 2 | OD | Hollick
Study Learning Ctr | 00-08575.00 | 202390285 | 548226 | 0982-004 | Compressor Replacement | Building Permit |  | 2023-04-05 | 1 | OD | Hollick, Drasher
YORK CAMPUS 0964-000